## 05Qtr4
|  | Code | Actions
Action Plan Listing Q4 2005-6 |  |  | Target
Action complete
Project: EQUAL Project |  |  | Action overdue
Staff member: Claire Mitchell
| overdue | Week ending
Task planning |  | 2006-01-06 | 2006-01-13 | 2006-01-20 | 2006-01-27 | 2006-02-03 | 2006-02-10 | 2006-02-17 | 2006-02-24 | 2006-03-03 | 2006-03-10 | 2006-03-17 | 2006-03-24
Budget
Collation of Overheads and Indirect Expenditure | bar: 2006-01-06
Collation of other Expenditure | bar: 2006-01-27; 2006-02-24; 2006-03-24
Circulation and completion of Time Sheets | bar: 2006-01-06; 2006-01-27; 2006-02-24; 2006-03-24
Creation of BUDGET | bar: 2006-01-27
Submission of monthly claim form | bar: 2006-01-13; 2006-02-17
Submission of Forward Funding Form | bar: 2006-01-06; 2006-03-24
Match Funding Contracts Signed | bar: 2006-02-10 to 2006-03-24
Budget Review | bar: 2006-01-27; 2006-02-24; 2006-03-24
Create EE monitoring forms
Outcome + target (eg no. attending/achieved)
Budget agreed by EQUAL | bar: 2006-01-27
Finance
Set up EQUAL in QuickBooks | bar: 2006-01-13
Set up Petty Cash System | bar: 2006-01-13
Buy a petty cash box | bar: 2006-01-06
Enter current info into QuickBooks and maintain | bar: 2006-01-27
Outcome + target (eg no. attending/achieved)
Ensure Accounting System is up-to-date | bar: 2006-01-27; 2006-02-24; 2006-03-24
EEG Strategic Group (SEEG)
Elect and confirm members | bar: 2006-01-13
Attend and minute meeting | bar: 2006-02-24
Create new terms of reference | bar: 2006-02-10
Send out minutes | bar: 2006-03-03
confirm my role | bar: 2006-01-20
Creation of quarterly EEG Report | bar: 2006-02-03
Outcome + target (eg no. attending/achieved)
Meeting Agenda set for year | bar: 2006-02-24
EEG Operational Group (OEEG)
Introduce myself to EQUAL projects | bar: 2006-01-06
Set up meetings with each project | bar: 2006-01-20 to 2006-02-24
Map employer engagement locally | bar: 2006-01-20 to 2006-03-24
Create EE form | bar: 2006-01-06
Set dates for monthly meetings | bar: 2006-01-27
Create a terms of reference | bar: 2006-03-10
Attend and minute meeting | bar: 2006-03-10
Send out minutes | bar: 2006-03-17
Organise Agenda for training/seminars | bar: 2006-02-17; 2006-03-24
Set up training sessions x 9 | bar: 2006-03-24
Outcome + target (eg no. attending/achieved)
Achieve smooth running of OEEG | bar: 2006-03-24
Ensure all projects understand the concept of Equal & provide the skills required for sustainability | bar: 2006-03-24
CommunityMark
Confirm the level of personal involvement | bar: 2006-01-13
Identify relevant members of the OEEG for role out | bar: 2006-01-27
Create suitable marketing for role out | bar: 2006-03-24
Set up a monitoring system | bar: 2006-02-24
Outcome + target (eg no. attending/achieved)
Organise training for role out of CommunityMark | bar: 2006-03-24
EQUAL Business Sign Ups
Contact businesses | bar: 2006-01-20
Set a meeting up | bar: 2006-01-27; 2006-02-24
Outcome + target (eg no. attending/achieved)
Get them signed up to CommunityMark and working with an EQUAL project | bar: 2006-02-24 to 2006-03-24
Funding Support for continuation of Karen's post
Identify potential funders
Get confirmation from Terry Roy at EQUAL whether can have funding support | bar: 2006-01-06
Outcome + target (eg no. attending/achieved)
Support Thea in getting funding continuation for someone in this role | bar: 2006-01-20 to 2006-03-24
Management of Karen
Set up of weekly meetings
Monthly Personal Development Meetings | bar: 2006-01-27; 2006-02-24; 2006-03-24
Evaluate % of time allocated to EQUAL | bar: 2006-01-27; 2006-02-24; 2006-03-24
Outcome + target (eg no. attending/achieved)
Have a happy Karen
Operational Costs
Phones | bar: 2006-01-06
Evaluate need and cost for second line | bar: 2006-01-13
Buy a printer | bar: 2006-01-13
Buy annual bus pass | bar: 2006-01-20
Outcome + target (eg no. attending/achieved)
To have project infrastructure in place | bar: 2006-01-27
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)

## 06Qtr 1
|  | Code | Actions
Action Plan Listing Q1 2006-7 |  |  | Target
Action complete
Project: | EBH04 |  | Action overdue
Staff member: | Claire Mitchell
| overdue | Week ending
Task planning |  | 2005-04-01 | 2005-04-08 | 2005-04-15 | 2005-04-22 | 2005-04-29 | 2005-05-06 | 2005-05-13 | 2005-05-20 | 2005-05-27 | 2005-06-03 | 2005-06-10 | 2005-06-17 | 2005-06-24
Budget Completion
Get Match funders agreed and signed up | bar: 2005-05-06 to 2005-06-03
Budget agreed by Equal Core | bar: 2005-05-06 to 2005-06-03
Create match funding spreadsheet for monitoring | bar: 2005-04-01
Diarise collection of time sheets from relevant parties. | bar: 2005-04-01
Operational EEG Group
Set Meeting Dates | bar: 2005-04-08; 2005-05-06; 2005-06-03
Organise Venue | bar: 2005-04-01; 2005-04-22; 2005-05-20
Organise Catering | bar: 2005-04-01; 2005-04-22; 2005-05-20
Send out Minutes | bar: 2005-04-15; 2005-05-13; 2005-06-10
Workforce Development Strategy Group
Create Reports | bar: 2005-05-06
Attend Meeting | bar: 2005-05-13
Local Employer Engagement Organisations
Meet and qualify entry into OEEG
Introduce Equal to local Business Associations
Financial Monitoring
Over seeing financial monitoring
Manage Budget Spreadsheet
Manage monthly Equal claims
Equal Core
Keep monitoring reports accurate | bar: 2005-04-08; 2005-05-13; 2005-06-10
Regular contact with Kellee Rich re PR/marketing and comms
Attend weekly team meetings
Carry out research into Employer Engagement | bar: 2005-04-15
BCP
Attend weekly team meetings
EE Training Session
Health & Safety Workshop | bar: 2005-04-15; 2005-06-03
Organise a venue | bar: 2005-04-01; 2005-05-20
Organise catering | bar: 2005-04-01; 2005-05-20
Send out Minutes | bar: 2005-04-29; 2005-06-10
Outcome + target (eg no. attending/achieved)
Management of Karen
Set up of weekly meetings
Monthly Personal Development Meetings | bar: 2005-04-29; 2005-05-27; 2005-06-24
Evaluate % of time allocated to EQUAL | bar: 2005-04-29; 2005-05-27; 2005-06-24
Outcome + target (eg no. attending/achieved)
Have a happy Karen
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)

## 06Qtr 2
|  | Code | Actions
Action Plan Listing Q2 2005-6 |  |  | Target
Action complete
Project: |  |  | Action overdue
Staff member:
| overdue | [6 empty] | Week ending
Task planning |  | 2005-07-01 | 2005-07-08 | 2005-07-15 | 2005-07-22 | 2005-07-29 | 2005-08-05 | 2005-08-12 | 2005-08-19 | 2005-08-26 | 2005-09-02 | 2005-09-09 | 2005-09-16 | 2005-09-23 | 2005-09-30
Budget Completion
Get Match funders agreed and signed up | bar: 2005-07-01 to 2005-09-02
Budget agreed by Equal Core | bar: 2005-07-01 to 2005-09-02
Diarise collection of time sheets from relevant parties. | bar: 2005-07-01
Operational EEG Group
Hold Meeting | bar: 2005-07-08; 2005-09-09
Organise Venue | bar: 2005-07-01
Organise Catering | bar: 2005-07-01; 2005-09-02
Send out Minutes | bar: 2005-07-15; 2005-09-16
Workforce Development Strategy Group
Create Reports | bar: 2005-07-15; 2005-09-02
Attend Meeting | bar: 2005-07-22; 2005-09-09
Local Employer Engagement Organisations
Meet and qualify entry into OEEG
Introduce Equal to local Business Associations
Financial Monitoring
Over seeing financial monitoring
Manage Budget Spreadsheet
Manage monthly Equal claims
Equal Core
Keep monitoring reports accurate | bar: 2005-07-15; 2005-08-12; 2005-09-16
Attend weekly team meetings
BCP
Attend weekly team meetings
EE Training Sessions
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Management of Karen
Set up of weekly meetings
Monthly Personal Development Meetings | bar: 2005-07-29; 2005-08-26; 2005-09-23
Evaluate % of time allocated to EQUAL | bar: 2005-07-29; 2005-08-26; 2005-09-23
Outcome + target (eg no. attending/achieved)
Have a happy Karen

## 06Qtr 3
|  | Code | Actions
Action Plan Listing Q3 2005-6 |  |  | Target
Action complete
Project: |  |  | Action overdue
Staff member:
| overdue | Week ending
Task planning |  | 2005-10-07 | 2005-10-14 | 2005-10-21 | 2005-10-28 | 2005-11-04 | 2005-11-11 | 2005-11-18 | 2005-11-25 | 2005-12-02 | 2005-12-09 | 2005-12-16 | 2005-12-23 | 2005-12-30
Budget Completion
Get Match funders agreed and signed up | bar: 2005-10-07 to 2005-12-09
Budget agreed by Equal Core | bar: 2005-10-07 to 2005-12-09
Operational EEG Group
Set Meeting Dates | bar: 2005-10-07; 2005-11-04; 2005-12-09
Organise Venue | bar: 2005-10-07; 2005-10-28; 2005-12-02
Organise Catering | bar: 2005-10-07; 2005-10-28; 2005-12-02
Send out Minutes | bar: 2005-10-14; 2005-11-04; 2005-12-16
Workforce Development Strategy Group
Create Reports | bar: 2005-12-02
Attend Meeting | bar: 2005-12-02
Local Employer Engagement Organisations
Meet and qualify entry into OEEG
Introduce Equal to local Business Associations
Financial Monitoring
Over seeing financial monitoring
Manage Budget Spreadsheet
Manage monthly Equal claims
Equal Core
Keep monitoring reports accurate | bar: 2005-10-14; 2005-11-11; 2005-12-09
Attend weekly team meetings
BCP
Attend weekly team meetings
EE Training Sessions
CommunityMark Training Session | bar: 2005-12-09
Organise a venue | bar: 2005-12-02
Organise catering | bar: 2005-12-02
Send out Minutes/Papers | bar: 2005-12-16
Outcome + target (eg no. attending/achieved) |  | 2005-12-09: 10
Management of Karen
Set up of weekly meetings
Monthly Personal Development Meetings | bar: 2005-11-04; 2005-12-02; 2005-12-30
Evaluate % of time allocated to EQUAL | bar: 2005-11-04; 2005-12-02; 2005-12-30
Outcome + target (eg no. attending/achieved)
Have a happy Karen
Project Evaluation
Commission a company to do the work | bar: 2005-10-07
Inform Relevant OEEG & WFDEES G Members | bar: 2005-10-07
Invite evaluator to an OEEG Meeting | bar: 2005-11-04; 2005-12-02
Circulate the completed report | bar: 2005-12-16
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)
Key area task
Task
Task
Task
Task
Outcome + target (eg no. attending/achieved)

## 06Qtr4
|  | Code | Actions
Action Plan Listing Q4 2005-6 |  |  | Target
Action complete
Project: EQUAL Project |  |  | Action overdue
Staff member: Claire Mitchell
| overdue | Week ending
Task planning |  | 2006-01-06 | 2006-01-13 | 2006-01-20 | 2006-01-27 | 2006-02-03 | 2006-02-10 | 2006-02-17 | 2006-02-24 | 2006-03-03 | 2006-03-10 | 2006-03-17 | 2006-03-24
Budget Completion
Get Match funders agreed and signed up | bar: 2006-01-06 to 2006-03-10
Budget agreed by Equal Core | bar: 2006-01-06 to 2006-03-10
Operational EEG Group
Set Meeting Dates | bar: 2006-01-06; 2006-02-03; 2006-03-10
Organise Venue | bar: 2006-01-06; 2006-01-27; 2006-03-03
Organise Catering | bar: 2006-01-06; 2006-01-27; 2006-03-03
Send out Minutes | bar: 2006-01-13; 2006-02-03; 2006-03-10
Workforce Development Strategy Group
Create Reports
Attend Meeting
Local Employer Engagement Organisations
Meet and qualify entry into OEEG
Introduce Equal to local Business Associations
Financial Monitoring
Over seeing financial monitoring
Manage Budget Spreadsheet
Manage monthly Equal claims
Equal Core
Keep monitoring reports accurate | bar: 2006-01-13; 2006-02-10; 2006-03-10
Attend weekly team meetings
BCP
Attend weekly team meetings
EE Training Sessions
JCP/Working Links Benefits Workshop | bar: 2006-01-13
Organise a venue | bar: 2006-01-06
Organise catering | bar: 2006-01-06
Send out Minutes/Papers | bar: 2006-01-20
Alliantist Partnership Workshop | bar: 2006-02-10
Organise a venue | bar: 2006-01-27
Organise catering | bar: 2006-01-27
Send out Minutes/Papers | bar: 2006-02-17
Outcome + target (eg no. attending/achieved)
Management of Karen
Set up of weekly meetings
Monthly Personal Development Meetings | bar: 2006-02-03; 2006-03-03
Evaluate % of time allocated to EQUAL | bar: 2006-02-03; 2006-03-03
Outcome + target (eg no. attending/achieved)
Have a happy Karen