| Task / Activity | Priority | What tasks need to be completed to achieve this? | Who? |  | Resources needed? |  | Due date? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Engage Meetings |  |  |  |  |  |  |  |
| Monthly Forums in Brighton & Hove | HIGH | - Date Organised - Venue Organised - Minutes Taken - Minutes Circulated | CM CM JCP JCP/CM |  | - CM’s Time - F.O.C Venues across the City - JCP Staff Member |  | Ongoing |
| EE Forum |  |  |  |  |  |  |  |
| Manage the EE Forum for Engage Members | HIGH | - Set up a ‘e-List’ with all members emails - Record circulated messages & queries | CM/TR Admin |  | - Terry’s Time - Software - Claire’s Time - Admin’s Time |  | July 07 |
| EE Reports |  |  |  |  |  |  |  |
| Monthly Update Reports for Engage Bi-Monthly Reports for WFDG Monthly Hospitality Futures Reports | MED | - Collation of information - Write Reports - Present Reports - Circulate Reports | CM | - Claire’s Time |  | Ongoing |  |

| Task / Activity | Priority | What tasks need to be completed to achieve this? | Who? | Resources needed? | Due date? |
| --- | --- | --- | --- | --- | --- |
| Argus Placement Table |  |  |  |  |  |
| Monthly Placement Table depicting all the local businesses signing up to work placements & employment of Engage clients | MED | - Reminder to all Engage members to submit details of business signed up each month - Collation of the date into spreadsheet - Email to James Lancaster at The Argus on the second to last Tuesday of each month | Admin Admin CM | - Admin’s Time - Admin’s Time - Claire’s Time | Monthly |
| Engage Website |  |  |  |  |  |
| Engage Website to contain all related information, links to members’ website and sponsor info | LOW | - Get 3 quotes for project - Select Best Value - Agree Design - Agree Content - Place all content on site - Roll Out | Claire Claire Claire Claire Admin Engage | - Claire’s Time - Admin’s Time - Engage’s Time | Jul – Dec 07 |
| Hospitality Futures |  |  |  |  |  |
| Deliver Hospitality Futures Project | HIGH | - Please see HF project plan | Claire | - Claire’s Time | Jul – Dec 07 |

| The Argus Job Fair |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Engage & The Argus working in partnership to deliver The Argus Job Fair | MED | - Agreement signed outlining partnership - Engage members to recruit employers and clients to the Fair - The Argus to promote the Fair in the press - Engage members to promote the Fair in the local community - Engage to get a F.O.C stand at the Event for members - JCP to fund a shelf scheme to hold interviews with clients on the day - Engage members to assist employers to man their stands - Engage members to provide roving support on the day | CM/JCP/The Argus Engage The Argus Engage The Argus JCP Engage/JCP Engage | Claire/Brendon Walsh/Rhys Trussler’s time | Jul – Sept 07 |