Engage RBLI/Working Links Contract

Claire Mitchell

15th February 2008

## Update

I thought it would be useful for us if I did a quick précis of what we discussed this afternoon.

The proposed start date is between mid April to May 1st 2008 and the contract duration is 12 months, with all parties able to give 3 months notice.

We agreed a target of 300 job outcomes for the 12-month period; to be reviewed at each quarterly meeting.

The first quarter would need to generate 50 job outcomes

Long-term goals for the project include the delivery of PET programmes where possible; Butlins could be the pilot case, and the establishment of employer forums where necessary

CM will have autonomy in determining how these outcomes are met, i.e. whether the project officers will concentrate on specific sectors or otherwise

The project team will be primarily located at either RBLI or WL offices, each project officer will simply hot desk within a designated part of each office

CM will invoice both organisations at the beginning of each month to ensure that the funds have arrived in order to pay Laura Hampson; Engage is to new to have built up reserves to carry any upfront costs

RBLI/WL, as per the original proposal, will cover any expenses incurred by the project such as telephone costs, IT equipment etc

CM is able to discuss this at the next Engage Forum on the 20th February 2008

### Action Points

- RBLI/WL to report back on project specific branding – name/logo etc

- WL to circulate job descriptions to ALL

- Dates to be confirmed in advance for review meetings

- RBLI/WL to ensure Engage Employment Solutions is set up on their BACS system:

Account Number: 70813829

Sort Code: 08-92-50

Cooperative Bank

- The SLA will be reviewed by CM before it is signed off

- RBLI to confirm project start date

- RBLI/WL to ensure CM is involved in the recruitment process to ensure suitable candidates that will work well together are found