## Risk Analysis Template
Equal Project EBH04
Risk Analysis Template
[8 empty] | √ | Please copy & paste tick to relevant section
| Activity | Description of Risk | Probability of Risk (please tick one) |  |  | Impact of the Risk (please tick one) |  |  | Planned Action
|  |  | Low | Med | High | Low | Med | High
1 | Co-ordination of Employer Engagement (EE) in the City | Project does not continue past June 2007 due to lack of continuation funding. This will affect Engagemembers' ability to continue to work in partnership, resulting in service users not being referred to the correct support services, which will lead to less service users returning to work |  |  | √ |  |  | √ | To find continuation funding with the support of the Workforce Development Strategy Group (WFDS Group)
2 | Strategic targeting of local businesses for EE | Project does not continue past June 2007 due to lack of continuation funding. This could lead to businesses disengaging through constant targeting pressure and other potential placement providers never being contacted, thus not maximising market potential |  |  | √ |  |  | √ | To find continuation funding with the support of the Workforce Development Strategy Group (WFDS Group)
3 | Preventing duplication of services and isolation of agencies setting up in the City | Project does not continue past June 2007 due to lack of continuation funding. New supported employment agencies setting up in the City would be unaware of existing services and protocols resulting in potential duplication of services and increased competitive working in an already overly competitive market - 8,500 registered businesses - 13,000 placements required each year |  |  | √ |  |  | √ | Member of the WFDS Group to take responsibility for maintaining the Engage Directory and ensure all new services are made aware
4 | One Stop Shop for EE in the City | Project does not continue past June 2007 due to lack of continuation funding. This would result in organisations and businesses wishing to collectively target organisations involved in EE not being able to do so |  |  | √ |  |  | √ | Member of the WFDS Group to take responsibility for maintaining the Engage Directory to provide all contact details
5 | Universal Standards & Best Practice | Project does not continue past June 2007 due to lack of continuation funding. No group to develop and police the universal standards of practice in EE to ensure quality and consistency, resulting in varying levels of service and more confusion and time taken for local businesses. This could lead to the disengagement of businesses, resulting in lower numbers of service users accessing employment |  |  | √ |  |  | √ | To find continuation funding with the support of the Workforce Development Strategy Group (WFDS Group)
6 | Training Sessions | Project does not continue past June 2007 due to lack of continuation funding. No service to provide and source training to supported employment agencies, resulting in historic lack of staff training and development in this area, resulting in staff not being up to date with recent changes in EE legislation, not suitably trained to successfully support service users into employment and potentially putting service users in high risk situations by being ignorant of the risks and motivated purely by achieving targets |  |  | √ |  |  | √ | To find continuation funding with the support of the Workforce Development Strategy Group (WFDS Group)
7 | EE Forum | Project does not continue past June 2007 due to lack of continuation funding. There will not be a collective approach to circulating opportunities and requests in the field, leading to loss of opportunity and knowledge sharing |  |  | √ |  |  | √ | Member of the WFDS Group to take responsibility for maintaining the OEEG EE Forum
8 | OEEG Member Motivation & Morale | Project does not continue past June 2007 due to lack of continuation funding. This could lead to loss of morale and motivation of the current OEEG members that has been generated by the work of the group to date |  |  | √ |  |  | √ | All the salient information gathered by the OEEG to be put into a Best Practice Guide to EE in the City for June 2007
9 | Consistency of Project Manager role | Current Project Manager leaving post. There would be difficluty finding a replacement due to the specialist skills and expertise required for the post, including the knowledge accrued to date. This would potentially have a serious impact on the smooth running and success of the project |  |  | √ |  |  | √ | Re-evaluate qualifications and experience required for the post. Ensure all procedures are in place to enable smooth transition between workers. Regular appraisals / meetings to identify potential issues. Ensure funds are available to find suitable replacement
10 | Consistency of Project Officer role | Current Project Officer leaving post. There may be difficulty finding a suitable replacement due to the skills and expertise required for the post, including the knowledge accrued to date. This could potentially have a serious impact on the smooth running of the project |  | √ |  |  | √ |  | Identify qualifications and experience needed to fill this post. Clear list of procedures and duties associated with the role to ensure smooth transition between workers. Regular appraisals / meetings to identify potential issues. Ensure funds are available to find a suitable replacement

## Procedure
Risk Analysis Procedure
Risk management is a continuous process that starts during the initiation of the project and proceeds until the project is completed. Three types of risk: 1. Known Risks - risks that can be identified, we can draw from experience 2. Predictable Risks - risks that might occur, anticipated risks based on other similar projects, based on instincts rather than something concrete (staff turnover, economic change etc) 3. Unpredicatble Risks - things beyond the control of the project manager or team
Steps to Manage Risks Make a list of risks and describe their potential impact. Analyse the probability of the risk occuring and determine the impact of the risk. Determine what risks are most important / require further action. There are four basic options 1. Accept the risk; if and when it emerges, the team will deal with it 2. Avoid the risk; delete the part of the project which contains the risk 3. Monitor the risk and develop a contingency plan; developing contingency plan for key risks is one of the most important aspects of risk management 4. Transfer the risk; insure or sub contract Please Note Risks must be regularly re-evaluated