## Risk Analysis Template
Equal Project EBH04
Risk Analysis Template
[8 empty] | √ | Please copy & paste tick to relevant section
| Activity | Description of Risk | Probability of Risk (please tick one) |  |  | Impact of the Risk (please tick one) |  |  | Planned Action
|  |  | Low | Med | High | Low | Med | High
1 | Project Management | Current Project Manager leaving post. There would be difficluty finding a replacement due to the specialist skills and expertise required for the post, including the knowledge accrued to date. This would potentially have a serious impact on the smooth running and success of the project |  |  | √ |  |  | √ | Re-evaluate qualifications and experience required for the post. Ensure all procedures are in place to enable smooth transition between workers. Regular appraisals / meetings to identify potential issues. Ensure funds are available to find suitable replacement
2 | Project Operations | Current Project Officer leaving post. There may be difficulty finding a suitable replacement due to the skills and expertise required for the post, including the knowledge accrued to date. This could potentially have a serious impact on the smooth running of the project |  | √ |  |  | √ |  | Identify qualifications and experience needed to fill this post. Clear list of procedures and duties associated with the role to ensure smooth transition between workers. Regular appraisals / meetings to identify potential issues. Ensure funds are available to find a suitable replacement
3 | Sustainability | The project model becomes out of date and ineffective |  | √ |  |  | √ |  | Develop the project model building in research, monitoring and reviewing procedures to ensure that the service offered is up to date, effective and efficient. Develop and maintain links with all key strategic bodies and stakeholders.
4 | Duplication of Service | Another provider offers similar service in geographic area |  | √ |  |  |  | √ | Develop and maintain links with key strategic bodies locally. Continue to promote services and brand awareness with all organisations involved in employer engagement, highlighting the benefits of the independence of this type of group. Link with all large businesses, statutory organisations and business forums
5 | Buildings | Long term availability of identified office space |  | √ |  | √ |  |  | Create procedure if organisation is given notice to move. List potential office space and meeting room / work station availability locally (short term solution)
6 | Service Charges | Exclusion of some organisations from the group / training due to the introduction charges for membership / training | √ |  |  | √ |  |  | Charges will only be introduced after full consultation between members and key stakeholders. Membership charges will be kept as low as possible, with a tier structure in place relating to business size and services to be included. Training will be sourced using the Best Value procedure and reduced rates will be negotiated.
7 | Business Engagement | Businesses do not engage or disengage |  | √ |  |  |  | √ | Clear brand, marketing and PR showing the business benefits of engaging. Continue to identify and offer training to OEEG members. Single point of contact for businesses - work towards a single account management strategy for employer engagement so businesses. Research and taking into account the various sizes, sectors, requirements and expectations.
8 | Continued funding for Employer Engagement Activities | Change in the Government Agenda - currently employer engagement is high on the government agenda but this could be affected by a change in leadership | √ |  |  | √ |  |  | Ensure that relationships are continued at a local strategic level as information is fed in at national level. Develop links with key governing bodies and government sponsored organisations. React internally to small changes in government agenda by continually reviewing and developing the project model
9 | Continued funding for Employer Engagement Activities | Economic Recession - this would affect funding to OEEG organisations and impact on the amount of businesses offering work placements |  | √ |  |  |  | √ | Develop marketing strategy to businesses to clearly show the financial benefits of engaging. Keep up to date with the national and local economic forecasts and regularly consult with all key stakeholders all key stakeholders
10 | Brand Recognition | Unclear branding for the Operational Employer Engagement Group (OEEG); the name is not user friendly and very 'public sector', which may affect its profile and development |  | √ |  |  |  | √ | Re-name the Engage. Instruct a marketing expert to re-brand the group; create a logo, develop clear marketing literature, launch a user-friendly website and hold a re-launch event for all stakeholders and local businesses
11 | Press and Publicity | Bad publicity and poor performance of employer engagement / OEEG / OEEG organisations may impact on success of the project; key stakeholders especially business and service user involvement |  | √ |  |  |  | √ | Continue to build good relationships with media. Continue to present the work of the Engage to business organisations. Monitoring systems in place to identify, investigate and resolve issues, ensuring procedure is in place to react to bad publicity. Continue to liaise with Engage members to develop standards around employer engagement. Regular meetings to raise issues with all stakeholders.

## Procedure
Risk Analysis Procedure
Risk management is a continuous process that starts during the initiation of the project and proceeds until the project is completed. Three types of risk: 1. Known Risks - risks that can be identified, we can draw from experience 2. Predictable Risks - risks that might occur, anticipated risks based on other similar projects, based on instincts rather than something concrete (staff turnover, economic change etc) 3. Unpredicatble Risks - things beyond the control of the project manager or team
Steps to Manage Risks Make a list of risks and describe their potential impact. Analyse the probability of the risk occuring and determine the impact of the risk. Determine what risks are most important / require further action. There are four basic options 1. Accept the risk; if and when it emerges, the team will deal with it 2. Avoid the risk; delete the part of the project which contains the risk 3. Monitor the risk and develop a contingency plan; developing contingency plan for key risks is one of the most important aspects of risk management 4. Transfer the risk; insure or sub contract Please Note Risks must be regularly re-evaluated