## Project_Details (hidden)
Project Number | EBH004
Project Name | BHBCP

## Summary
Aims | Strategic objectives | Inputs | Outputs | Performance Indicators | Outcomes
1.1 To facilitate labour market access for hard-to-reach local residents, by liasing with all organisations in Brighton & Hove that are actively engaging with employers, promoting joined-up-working in order to deliver a more prefessional and coordinated approach. | 2.1 Monthly meetings on with employer engagement workers. |  | 4.1 Minuted meetings 4.2 Evaluation forms 4.3 News and information service (email) 4.4 Terms of reference | 5.1 20 or more attendees per session. 5.2 15 or more evaluations returned per session. 5.3 Signed copies of terms of reference for all members. | 6.1 An authoritative guide on employer engagement in Brighton & Hove produced and available for mainstreaming.
| 2.2 Deliver 9 employer engagement training sessions. |  | 4.5 Booked venues 4.6 Speakers 4.7 Content 4.8 Evaluation forms 4.9 Training (to competence standard) | 5.4 10 or more attendees per training session. 5.5 100% completion of evaluation forms. 5.6 At least 1 information resource/handout or material per session. | 6.2 All organisations involved working in sustainable partnership.
| 2.3 Sector mapping exercise with 40 organisations actively engaged with employer engagement, towards the production of an Employer Engagement Directory. |  | 4.10 Flow charts 4.11 1:1 visits 4.12 Information forms 4.13 OEEG members contact lists | 5.7 20(+) information forms collected. 5.8 20 organisations submit membership contacts list. | 6.3 Placement officers using standardised and effective paperwork processes.
| 2.4 Create best practice guide to employer engagement in Brighton & Hove. |  | 4.14 Employer Engagement Conference (TBC) 4.15 1x handbook (design, content, printing, distribution) | 5.9 250 copies of handbook to all organisations and stakeholders. 5.10 Guide available to interested parties for mainstreaming purposes. | 6.4 Barriers to employment faced by hard-to-reach groups reduced, and more hard to reach beneficiaries getting into empoyment.

## Project Aims
# | Section 1: Aims | Spacer1 | Spacer1 | Clarification | Spacer1 | Revised Aims | Spacer1 | Additional Aims | For Administrative Use Only | Line
1 | To facilitate labour market access for hard-to-reach local residents, by liasing with all organisations in Brighton & Hove that are actively engaging with employers, promoting joined-up-working in order to deliver a more prefessional and coordinated approach. | [8 empty] | 1.1 | Section: | 1

## Strategic Objectives
Obj# | Section 2: Strategic Objectives (SOs) | Spacer1 | Spacer1 | Clarification | Spacer2 | Revisions to Strategic Objectives | Spacer2 | Additional Strategic Objectives | For Administrative Use Only | Line
1 | Monthly meetings on with employer engagement workers. | [8 empty] | 2.1 | Section: | 2
2 | Deliver 9 employer engagement training sessions. | [8 empty] | 2.2
3 | Sector mapping exercise with 40 organisations actively engaged with employer engagement, towards the production of an Employer Engagement Directory. | [8 empty] | 2.3
4 | Create best practice guide to employer engagement in Brighton & Hove. | [8 empty] | 2.4

## Inputs
# | Section 3: Inputs | Related to SO # | For Administrative Use Only | Line
|  |  |  | Section: | 3

## Outputs
# | Section 4: Outputs | Related to SO# | Spacer1 | Clarification | Spacer4 | Revisions to Outputs | Spacer4 | Additional Outputs | Related to SO# (new output only) | For Administrative Use Only | Line
1 | Minuted meetings | 1 | [8 empty] | 4.1 | Section: | 4
2 | Evaluation forms | 1 | [8 empty] | 4.2
3 | News and information service (email) | 1 | [8 empty] | 4.3
4 | Terms of reference | 1 | [8 empty] | 4.4
5 | Booked venues | 2 | [8 empty] | 4.5
6 | Speakers | 2 | [8 empty] | 4.6
7 | Content | 2 | [8 empty] | 4.7
8 | Evaluation forms | 2 | [8 empty] | 4.8
9 | Training (to competence standard) | 2 | [8 empty] | 4.9
10 | Flow charts | 3 | [8 empty] | 4.10
11 | 1:1 visits | 3 | [8 empty] | 4.11
12 | Information forms | 3 | [8 empty] | 4.12
13 | OEEG members contact lists | 3 | [8 empty] | 4.13
14 | Employer Engagement Conference (TBC) | 4 | [8 empty] | 4.14
15 | 1x handbook (design, content, printing, distribution) | 4 | [8 empty] | 4.15

## Performance Indicators
# | Section 5: Performance Indicators (PIs) | Related to SO# | Spacer1 | Clarification | Spacer5 | Revisions to PIs | Spacer5 | Additional PIs | Related to SO# (use if new PI is added) | For Administrative Use Only | Line
1 | 20 or more attendees per session. | 1 | [8 empty] | 5.1 | Section: | 5
2 | 15 or more evaluations returned per session. | 1 | [8 empty] | 5.2
3 | Signed copies of terms of reference for all members. | 1 | [8 empty] | 5.3
4 | 10 or more attendees per training session. | 2 | [8 empty] | 5.4
5 | 100% completion of evaluation forms. | 2 | [8 empty] | 5.5
6 | At least 1 information resource/handout or material per session. | 2 | [8 empty] | 5.6
7 | 20(+) information forms collected. | 3 | [8 empty] | 5.7
8 | 20 organisations submit membership contacts list. | 3 | [8 empty] | 5.8
9 | 250 copies of handbook to all organisations and stakeholders. | 4 | [8 empty] | 5.9
10 | Guide available to interested parties for mainstreaming purposes. | 4 | [8 empty] | 5.10
11 | [10 empty] | 5.11
12 | [10 empty] | 5.12
13 | [10 empty] | 5.13
14 | [10 empty] | 5.14
15 | [10 empty] | 5.15
16 | [10 empty] | 5.16

## Outcomes
# | Section 6: Outcomes | Spacer1 | Spacer1 | Clarification | Spacer6 | Revision to Outcomes | Spacer6 | Additional Outcomes | For Administrative Use Only | Line
1 | An authoritative guide on employer engagement in Brighton & Hove produced and available for mainstreaming. | [8 empty] | 6.1 | Section: | 6
2 | All organisations involved working in sustainable partnership. | [8 empty] | 6.2
3 | Placement officers using standardised and effective paperwork processes. | [8 empty] | 6.3
4 | Barriers to employment faced by hard-to-reach groups reduced, and more hard to reach beneficiaries getting into empoyment. | [8 empty] | 6.4

## ADMIN_ONLY_Outputs (hidden)
Obj | Combined Output | Outputs
1 | 4.1 Minuted meetings 4.2 Evaluation forms 4.3 News and information service (email) 4.4 Terms of reference | 4.1 Minuted meetings | 4.2 Evaluation forms | 4.3 News and information service (email) | 4.4 Terms of reference
2 | 4.5 Booked venues 4.6 Speakers 4.7 Content 4.8 Evaluation forms 4.9 Training (to competence standard) |  |  |  | 4.5 Booked venues | 4.6 Speakers | 4.7 Content | 4.8 Evaluation forms | 4.9 Training (to competence standard)
3 | 4.10 Flow charts 4.11 1:1 visits 4.12 Information forms 4.13 OEEG members contact lists | [7 empty] | 4.10 Flow charts | 4.11 1:1 visits | 4.12 Information forms | 4.13 OEEG members contact lists
4 | 4.14 Employer Engagement Conference (TBC) 4.15 1x handbook (design, content, printing, distribution) | [10 empty] | 4.14 Employer Engagement Conference (TBC) | 4.15 1x handbook (design, content, printing, distribution)
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## ADMIN_ONLY_PIs (hidden)
Obj | Combined Pis | Pis
1 | 5.1 20 or more attendees per session. 5.2 15 or more evaluations returned per session. 5.3 Signed copies of terms of reference for all members. | 5.1 20 or more attendees per session. | 5.2 15 or more evaluations returned per session. | 5.3 Signed copies of terms of reference for all members.
2 | 5.4 10 or more attendees per training session. 5.5 100% completion of evaluation forms. 5.6 At least 1 information resource/handout or material per session. |  |  | 5.4 10 or more attendees per training session. | 5.5 100% completion of evaluation forms. | 5.6 At least 1 information resource/handout or material per session.
3 | 5.7 20(+) information forms collected. 5.8 20 organisations submit membership contacts list. |  |  |  |  | 5.7 20(+) information forms collected. | 5.8 20 organisations submit membership contacts list.
4 | 5.9 250 copies of handbook to all organisations and stakeholders. 5.10 Guide available to interested parties for mainstreaming purposes. | [5 empty] | 5.9 250 copies of handbook to all organisations and stakeholders. | 5.10 Guide available to interested parties for mainstreaming purposes.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24