# Evaluation of the Equal Brighton & Hove

# Employer Engagement Project

(AMMENDED FINAL VERSION 25.9.06)

#### Research proposal prepared by Brough Dann for

#### Claire Mitchell, Project Co-ordinator, September 2006

Contact: 	Siobhan Brough

Position: 	Director (Research)

Brough Dann

8 Queen Mary Avenue

Hove BN3 6XG

Tel:		01273 501537

Email:		siobhan@broughdann.com

# Introduction

The Equal Brighton & Hove Employer Engagement Project has been running since December 2005 and is currently funded until June 2007.  The project’s aim is to bring together and support the numerous employer engagement agencies in the city in order to network and share best practice, as well as representing these organisations strategically in the city and acting as a lobbying voice where this is needed.  The project currently has 44 member organisations (these form the Operational Employer Engagement Group – OEEG) and also feeds into the Workforce Development Employer Engagement Strategy Group.  The OEEG holds a monthly forum, and the Employer Engagement Project has organised a number of training sessions in areas such as Health & Safety and Public Relations for OEEG members.

As the Employer Engagement Project approaches its mid-point the co-ordinator would like to undertake an evaluation exercise, to ensure the project is maximising its potential within its given timeframe, and also to identify whether there are aspects of the project that could be continued beyond June 2007.

Brough Dann has been asked to prepare a proposal for the evaluation of the Employer Engagement Project, and this proposal is the result of an initial meeting between Siobhan Brough (Brough Dann) and Claire Mitchell (Brighton & Hove Equal Employer Engagement Project).

# Research Objectives

The key objective of the research is to evaluate the Employer Engagement Project in terms of its achievements to date and its potential for development both up to and beyond the project’s projected end date of June 2007.  Brough Dann would recommend that this evaluation focus on exploring the following areas:

- What change has been brought about by the existence of the project?  For example, what has been achieved in terms of;

  - Quantifiable gains, such as an increase in placements/jobs (where this has been monitored)

  - Qualitative gains, such as local employer engagement agencies feeling they have a stronger and more coherent ‘voice’ locally, or feeling more confident and skilled in their work as a result of more focused training opportunities and sharing of best practice

- What do stakeholders (particularly OEEG members) value about the Equal Employer Engagement project?

  - What role do they see it as fulfilling?

- Are there improvements to be made to the project?

  - Are there any operational issues, or is the project running smoothly?

  - If there are any issues, how could these be addressed?

- What can be learnt from the first half of the project’s timeframe?

  - If there have been difficulties, is there anything to learn about avoiding similar problems in the future?

  - Where the project has succeeded, what created this success? Are there useful lessons to take forward to future projects or agencies?

- Do stakeholders feel there is a role for the OEEG to continue beyond the end of the Employer Engagement Project in June 2007?

  - How might this function?

  - Would it be practical for the OEEG to charge a membership fee?

# Methodology

The research will be delivered through a combination of quantitative and qualitative methods, making use of existing monitoring data where appropriate.  The three main strands of the evaluation will be:

- A telephone survey with twenty stakeholders

- Four face to face interviews to explore issues in more depth

- Analysis of existing monitoring data

1. Telephone survey

A maximum of 20 interviews will be conducted with the following stakeholders:

- 14 representative organisations from the OEEG

- 2 members of the Workforce Development Strategy Group

- Director of the Business Community Partnership

- A representative of Equal

- 2 businesses who have become involved in employer engagement through the project

Brough Dann will work with the project co-ordinator on developing an appropriate sample of OEEG organisations to ensure the research is representative of membership. The survey will cover the main issues outlined in the Research Objectives on the previous page, i.e.:

- What change has been brought about by the existence of the project?

- What do stakeholders value about the Equal Employer Engagement Project?

- Are there improvements to be made to the project?

- Is there a need to sustain the service the project is currently providing?

2. Face to face interviews

Key themes that emerge from the telephone surveys will be explored through face to face interviews with a maximum of four members of the OEEG. These interviews could be used to develop case studies of individual organisations, or to explore specific themes in more depth.  This will be defined in consultation with the project co-ordinator. Initial findings from these and the telephone interviews will be discussed with the OEEG and consequent comments incorporated into the final report.

3. Analysis of existing monitoring data

The project’s progress is constantly monitored through various forms including tracking of staff activity; recording of any issues and how these have been addressed; evaluation forms from training events and feedback on the OEEG monthly forums.  This data will be explored and incorporated into the report, to ensure that the evaluation findings are firmly rooted in the day-to-day realities of running the project, and also to examine the overall picture of the project’s progress that this data provides.

# Timescale

Below is a suggested timescale for the evaluation. Costs are outlined on the following page.

| Week commencing ACTIVITY | 18th Sept | 25th Sept | 2nd Oct | 9th Oct | 16th Oct | 23rd Oct | 30th Oct | 6th Nov | 13th Nov | 20th Nov | 27th Nov | 4th Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agree project outline & cost | . |  |  |  |  |  |  |  |  |  |  |  |
| Design telephone survey |  | . |  |  |  |  |  |  |  |  |  |  |
| Circulate questions to stakeholders |  |  | . |  |  |  |  |  |  |  |  |  |
| Conduct telephone survey |  |  |  | . | . |  |  |  |  |  |  |  |
| Arrange F2F interviews |  |  |  |  | . | . |  |  |  |  |  |  |
| Design F2F interview guide |  |  |  |  |  | . |  |  |  |  |  |  |
| Conduct F2F interviews |  |  |  |  |  |  | . | . |  |  |  |  |
| Attendance at OEEG meeting |  |  |  |  |  |  |  | . |  |  |  |  |
| Interviews transcribed |  |  |  |  |  |  |  |  | . |  |  |  |
| Analysis of existing data |  |  |  |  |  |  |  |  | . |  |  |  |
| Analysis of all data & report writing |  |  |  |  |  |  |  |  |  | . | . |  |
| Delivery of final report |  |  |  |  |  |  |  |  |  |  |  | . |

# Budget

Below is a breakdown of project costs. Please note VAT is not included in the total below.

| Activity | Cost |
| --- | --- |
| Planning & project management | £300 |
| Telephone survey design | £300 |
| Telephone interviews x 20 (including data inputting) | £405 |
| Face to face interviews x 4; set up, run & transcribe | £565 |
| Attendance at OEEG meeting for briefing & feedback | £150 |
| Analysis of existing monitoring data | £600 |
| Analysis of research data & report writing | £1060 |
| TOTAL: | £3,380 + VAT |

Note

Brough Dann adheres to the Market Research Society Code of Conduct in all respects, including Data Protection.  No individuals will deliberately be identified in the research report, unless they specifically request that their comments be attributed.

# About Brough Dann

Brough Dann is a partnership between Bunty Dann and Siobhan Brough, supported by a team of high quality associates.  Brough Dann supports sustainable organisational development using research, training and mentoring.  All our services are fundamentally about the process of change: This could be a company using research to inform a change of direction; an organisation wanting to gain new understanding and skills or an individual looking for support and guidance through a period of change.

We pride ourselves in the high quality of our research, and our clients frequently commission further work or recommend us on to others.  Below is a quote from one of our regular clients after the completion of a recent project;

Brough Dann is very organised, and can work easily within tight timescales.  Good communication too – I always feel I know where I am on any project Brough Dann is working on. Siobhan has a great knack for condensing my random ideas into a workable survey – very impressive.

Cara Bowen, Business Development Manager,

Royal Pavilion, Libraries & Museums

Many of Brough Dann’s clients are based in Brighton & Hove, consequently we have built up excellent knowledge and networks across the city, bringing added benefits to the people we work with.

### Project personnel

The personnel for the Equal Brighton & Hove Employer Engagement Project Evaluation will be;

- Siobhan Brough	Project Director

- Esther Gill		Researcher

- Bunty Dann		Project Consultant

Details on the relevant experience of the team can be found on the following pages.

Siobhan Brough, Project Director

Siobhan will oversee all aspects of the project and be the main point of contact.  Siobhan has a commitment to developing the role of research as an integral part of business practice, and leads on the Research strand of Brough Dann.  As well as delivering research services to clients she also works closely with organisations who are undertaking self-evaluation, developing the confidence and skills they need.  Recent projects Siobhan has managed have included;

| Quality of Life & Green Spaces, Brighton & Hove City Council: Groundwork Feasibility Study | Research to assess stakeholder response to proposed establishment of a new environmental regeneration Trust. Research conducted through face to face interviews and an analysis of existing data. (2006) |
| --- | --- |
| Brighton & Hove City Libraries: Black & Minority Ethnic Groups | Focus groups to initiate a process of encouraging engagement with the local Library Services by black and minority ethnic residents and to inform the development of provision. (2006) |
| Brighton & Hove Museums: Exhibition Print research | Research to inform the development of virtual marketing strategies. Included postal survey with regular attenders and interviewer-led surveys with visitors to Brighton Museum & Art Gallery. (2006) |
| Preston Manor Adult Learners | Telephone interviews supported by a competitor analysis to test market potential of proposed new adult learner facilities. (2005) |
| Brighton Festival: Schering Sponsorship Evaluation | Arts & Business funded evaluation to inform the development of Brighton Festival sponsorship. Research included telephone interviews and in-depth interviews with key stakeholders. (2005) |

Siobhan is a member of the Social Research Association and an Associate of The Market Research Society.

Esther Gill, Researcher

Esther will work with Siobhan on the project – primarily on the telephone contact and face to face interviews with stakeholders – and will contribute to the final report. Esther is a freelance researcher and writer and has extensive experience of working in the voluntary and community sector, with a particular interest in widening participation in community arts and heritage projects. Prior to working freelance, Esther worked as a Fundraising Manager for Sight Savers International and the Development and Marketing Manager for Carousel, a Brighton-based charity working with people with learning disabilities. Since 2001, Esther has worked freelance on a wide range of research, development and marketing projects. Recent projects that Esther has managed or worked on include:

| English Heritage / National Trust | Programming and coordinating a series of 20 workshops for an English Heritage/National Trust conference on widening participation in heritage. (2006) |
| --- | --- |
| Brighton & Hove City Council | Evaluation of the Say Aah Arts and Health Programme. (2004-05) |
| Same Sky | Evaluation of two participatory arts programmes. (2005) |
| West Sussex County Council | A series of surveys into role of the arts and heritage sector in the economies of the seven districts and boroughs of West Sussex. (2002-06) |

Esther is currently working towards an MA in Life History Research, specialising in oral history and individual accounts of past experiences.

Bunty Dann, Project Consultant

Bunty will be supporting Siobhan & Esther during the project.  Bunty’s experience in project management is extensive, with many of the projects she has worked on being pioneering in their nature, often bringing together diverse consortiums and partnerships to work together on agreed objectives, using creative solutions to achieve this.  Recent consultancies have included Business Action on Homelessness, The Enterprise Agency and Business in Regeneration.

Bunty is a fellow of the Royal Society for the encouragement of Arts, Manufacturing and Commerce.

- END -

# www.broughdann.com

# 01273 501537