## To Do
Engage Employment Solutions
To Do List
Priority 1-4 (1=High) | Project | Description | Action / Update | Assigned To | Completion Date | Status
1 | LEP | Collate Mapping for all relevant departments | Workshops and information still to be collected | KB
1 | LEP | Update Mapping spreadsheet | Add nil returns to mapping? E.g Vol Sector Unit
3 | LEP | Book meeting post April with John Routledge | To discuss LEP - mapping complete
2 | LEP | Create paper folder for LEP workshops - sign in etc |  | KB
2 | LEP | Re-schedule meeting with Cityclean - Renee Sturch re ringfenced jobs | Sent e-mail - awaiting response | KB
2 | LEP | Mapping to be sent to Housing | Wait until after meeting with Nick Hibberd and Helen Furlong | KB
2 | LEP | Await mapping from Adult Social Care |  | KB
2 | LEP | Identify who else requires the mapping document |  | KB
2 | LEP | Send mapping to Lance? | Discuss with Claire | KB
2 | LEP | Await mapping from Judith Drury to add to collation sheet | Chase up from 04/03 | KB
1 | LEP | Send mapping questionnaire and spreadsheet to Liz Morgan to circulate to Customer Services |  | KB
1 | LEP | Await approval of report from Customer Service | Jayne Fox and Pat amendments received. Awaiting Chris Fossey, Paul Holloway, Judith Street, Graham Bourne | KB
2 | LEP | Add refugee project to mapping details?? | Not successful bur discuss with Shaun re mapping | KB
2 | LEP | Take over Engage prep | Await infrastructure meeting with Claire
2 | LEP | EE Forum | Procedure
2 | LEP | Finance | Take over small aspects from Claire e.g. petty cash, invoices etc
2 | LEP | Strap Line for LEP on workshop notes | Create notes
2 | LEP | Planning tool for PET | Await infrastructure meeting with Claire
2 | LEP | LEP Awards Brief | Create brief to submit to Claire then on to Shaun | KB | 2008-04-11
2 | LEP | LEP Awards | Send in Awards Nomination (deadline for receipt 02/05/08) | CM/KB | 2008-04-28
1 | LEP | TMT Meeting Report | Create Template and write up report for Shaun | KB | 2008-03-07
1 | Career Moves | Career Moves Name Badges | Create name badges for Career Moves | KB | 2008-03-04
1 | LEP | Admin all Areas / Care Crew Briefing document | Create document for Engage Partnership re timescales/limitations..
1 | LEP | Mapping | Check mapping for duplicates | KB
3 | Engage | Admin Codes | Archive old admin codes / documents and change codes on current | KB
1 | Engage | Archive on files | Rename archive folder Z-Archive | KB
1 | Engage | Create Engage Partnership Procedure | See red book | KB
1 | Engage | EE Forum Procedure | See red book and email? | KB
1 | Engage | Meetings Spreadsheet | Create Meetings Spreadsheet | KB
1 | Engage | Engage website edit | Procedure to edit Engage website | KB

## To Buy
To Buy
Item | For Whom | Details | Purchase By Date | Status