Tourism Futures Proposal

- Vision

‘To improve the productivity of the tourism sector by maximising the engagement of local tourism-related employers in Government funded initiatives designed to support local residents into employment and to upskill existing employees’.

- Overview

Engage Employment Solutions Ltd (EES) will work directly with businesses and business forums to open up job opportunities by promoting the benefits of employing people from marginalised groups and encouraging corporate social responsibility.

This proposal is for a 10-month project focusing on:

- Engaging with tourism employers in the City with a view to involving them in the Tourism Forum

- Maintaining existing relationships with Tourism Forum members

- Managing and maintaining the Tourism Forum by setting up meetings, co-ordinating speakers and Chairing the meetings

- Carrying out the first phase of Tourism Futures Charter audits

- Assisting with sourcing employment vacancies for candidates going through the Tourism Futures Training Programme

- Partners

- Engage Employment Solutions Ltd (Lead)

- Brighton & Hove City Council – Economic Development

- Engage Partnership (Over 26 employment support agencies; including both Pathways and Train2Gain providers)

- City College Brighton & Hove - SOLD Project

- Working Links

- Related Strategies

- Tourism Strategy

- City Employment & Skills Plan (Brighton and Hove)

- Brighton & Hove’s Inequalities Review

- The Leitch Report

- Pathways

- Train2Gain

- Rationale

  - EES is a specialist employment broker with extensive experience of working directly with employers to determine their recruitment needs and promote diversity through the employment of disadvantaged people. EES has identified, through previous research (see Hospitality Futures Report December 2008), that the tourism sector is subject to very high staff churn rates and poor levels of customer service.

  - EES has been working with the tourism sector since July 2007 and has been responsible for both the development of the Tourism Futures Charter and the creation of the Tourism Forum.

  - To date the following businesses have signed the Charter and are members of the Tourism Forum:

- The De Vere Grand

- The Hilton Metropole

- The Thistle Hotel

- The Holiday Inn

- The Old Ship Hotel

- The Vienna Group (Queens Hotel etc)

- The Ramada Jarvis

- Hotel Alias Seattle

- Hotel du Vin

- Jurys Inns

- myhotel

- The Royal Albion

- The Lansdowne Hotel

- The Royal York Hotel

- Brighton Pier

- Paskins Hotel

- Proposal

  - EES to continue to manage the organisation and delivery of the Tourism Forum meetings; three will take place in the time frame for this project (July ‘08, Oct ‘08, Feb ‘09).

  - EES to continue to promote the Tourism Forum and remain the first point of contact for businesses. EES to carry out 1-2-1 meetings with potential members and increase membership numbers to a minimum of 25 active businesses.

  - EES to carry out Charter audit visits in December 2008 for all Tourism Forum members to determine which businesses will retain their Charter status.

  - EES to assist Working Links in the sourcing of at least 30 employment vacancies for candidates going through the Tourism Futures Training Programme.

  - EES to act as a sign post to other Tourism Futures Steering Group member services

- Marketing

The Project would be marketed through:

- The development of a specific website and logo (TBC)

- Existing Networks, such as the Engage Partnership

- Existing business networks, such as the Business Forum, Federation of Small Businesses, City College Business Club

- The Argus’s LEADER page when there is a relevant news story (first Tuesday of each month in the business section)

- Career Moves and The Argus Job Fair Events (4/annum)

- Web links on Tourism Futures Steering Group members’ websites

- Attending relevant business meetings to give presentations on the purpose of the Forum

- Cost

The budget for this service to be delivered from June 2008 until March 2009 has already been set by the funders, Brighton & Hove City Council and City College’s SOLD Project, at £20,000.

This amount will buy EES’s time for a maximum of 4 days per month.

The total cost, including VAT, will be £23,500

- Engage Breakdown of Services

9.1		Overview

Engage Employment Solutions Ltd is a specialist employment broker with extensive experience of working directly with employers to determine their recruitment needs and promote diversity through the employment of disadvantaged people.

The Engage team has a reputable history of designing and delivering innovative workforce solutions for employers, frequently acting as a broker between the public, voluntary and private sectors.

The team’s focus is on the employers’ needs; key strengths are the ability to work in partnership and decipher public sector speak to utilise existing government initiatives.

9.2	Services

The following services can be tailored to suit the organisation.

9.2.1	To Businesses:

- Advice and Guidance on how to recruit and retain a more diverse workforce

- Development and delivery of employment routes to target under-represented individuals

- Retention solutions to benefit the business and existing staff

- Free service to recruit for placements and/or employment

- Recognition of the commitment to diversity

- Networking and PR Opportunities

- Brokering job-specific and personal development training for new and existing staff, utilising government sponsored initiatives where possible

9.2.2	To Supported Employment Agencies:

- Advice and guidance

- Protocol and processes

- Placement and employment opportunities

- Training on 'How to engage employers'

- Marketing and public relations

- Health & Safety Risk Assessments

- Forum membership

- Joint funding applications

10.	Current Projects

10.1.1	The Engage Partnership – a highly innovative forum of over 26 employment support agencies. The members work together to increase the number of unemployed disadvantaged residents accessing sustainable employment through tailored training, mentoring, placement and employment initiatives. To compliment the outputs of each agency, the Engage Partnership has been directly responsible for generating over 250 vacancies.

    - The Tourism Forum – a ‘one stop shop’ for employment, training and networking opportunities, which is open to all businesses in the tourism sector. Members include the top thirteen hotels in the City and local tourist attractions, such as Brighton Pier. All are signed up to the Tourism Charter, which is a formal commitment to employ local people currently disengaged from the labour market. Engage specialises in translating public sector speak for businesses to access the wide range of government-funded initiatives.

    - The Brighton & Hove LEADER Group – Local Employers Acting on Diversity, Equality and Race. This is a new employer-led group set up to promote diversity in the City by developing best practice guidelines around staff recruitment and retention, training and development. The group hosts free events and workshops on all aspects of diversity for all businesses in the City. Any locally based business can sign up to LEADER Charter free of charge, which is a formal commitment to develop a more diverse workforce and employ from under-represented groups. This is a rapidly growing group of over twenty members and it is envisaged that the LEADER brand will be recognised as a diversity charter mark of distinction for all local employers.

    - Local Employment Partnership (LEP) – Engage has been commissioned to develop the framework and deliver on Brighton & Hove City Council’s LEP, which is a formal commitment to link with Jobcentre Plus to recruit a more diverse workforce. Engage works closely with its partners and across all Council departments to develop a supported route for marginalised individuals to access employment. Engage puts in place a robust sustainable model that builds on good practice and addresses issues around recruitment. The model further develops a culture of support, training and personal development within the organisation and embeds government initiatives, such as Train to Gain.

    - Engage 50+ Project – this is currently at bid stage and has been developed in partnership with Engage Partnership members and organisations, such as Age Concern and Brighton and Hove City Council (Sheltered Housing). The overall aim is to assist local residents who are fifty years old and over into employment through developing a routeway model to provide advice, guidance, training and support into employment. Engage is leading on this bid due to its specialism in working with employers and the team’s inside knowledge of sheltered housing.

11.	Track Record

To date the Engage Team have delivered the following products and services:

    - A well-known recent example of a successful workforce solution was the Constructing Futures Project, which generated over 50 construction apprenticeship placements, over 150 work placements and over 30 NVQ Assessors and formed an construction forum with key local employers

    - The Equal Brighton & Hove Engage Partnership and Best Practice Guide for Employer Engagement

    - The West Sussex Synchronise Forum (based on the Engage Partnership)

    - The Brighton & Hove LEADER Group

    - Employer engagement training to VT Careers

    - The Brighton & Hove City Council Local Employment Partnership Programme

    - The Brighton & Hove Tourism Forum and Charter

    - Employer engagement for both the Jury’s Inn and myhotel pre-employment training programmes

    - Direct generation of over 250 employment vacancies

## NB. References/testimonials can be obtained for any of these projects and services