BHCC LEP Project Meeting Report

Date: 5.02.08

Present: Shaun Rafferty (SR) - BHCC

Claire Mitchell (CM) – Consultant – Engage Employment Solutions Ltd

Actions:

- SR to confirm working age for child care -16 vs 18

- SR to contact Gillian Marston and arrange meeting for CM to discuss Parks & Gardens

- CM to arrange meeting with Maureen Passmore

- CM to create an activity map for SR to share with TMT

- CM to forward Lance Richard’s report for SR to use in Alan M’s briefing

- CM to approach Engage Forum to find out which agencies wish to deliver the LEP Training

- CM to look into recent email from Dan Shelley and report back if there is any impact on this work. CM meeting Dan on the 7th Feb.

- CM to contact Emma Gilbert to get a better understanding of her work in Housing with homeless people

- CM to produce fortnightly report for Alex Bailey