BHCC LEP Steering Group Update February 2008

Date: 26.02.08

Authors: Claire Mitchell (CM) – Engage Employment Solutions Ltd

Karen Barford (KB)  – Engage Employment Solutions Ltd

| Element | Activity | Status | Actions | Contact |
| --- | --- | --- | --- | --- |
| Terms of Reference | Needs Signing | Completed | During meeting | Steering Group |
| Phase 1: BHCC Ring Fenced Jobs to start in May 08 | Customer Services 4 Environment Parks & Gardens 4 Cityclean Recycling 4 Street Cleansing 4 Children’s Centres 1 per centre All will source 1 admin position over next 6 months Phase 1 – 20 jobs | Agreed | CM & KB to carry out workshops with each Department to identify exact roles and determine placement opportunities Customer Service – 28.02.08 Childrens Centres – 11.03.08 | Gillian Marston / Renee Sturch |
| PET 2 Week Programme | No LSC funding for Phase 1? Engage Members Rewards & Sussex Careers to deliver training but no further capacity at this stage beyond Phase 1 | Agreed | Training Rooms need to be sourced – no capacity within BHCC. Start date needs to be agreed – can only be last 2 weeks in April. Frequency needs to be agreed – tri-annually? | Steering Group |
| Assessment Day | Need to organise content; thought is to match literacy & numeracy needs against actual job and include questions about why person wants to work for BHCC. | Outstanding / Urgent | Room needs to be sourced for this – Brighton Town Hall looks to be the only potential venue and depends on dates | CM & KB |
| Placement Programme | It is the intention to maintain a placement service to allow those furthest from the labour market the opportunity for work tasters, which won’t affect their benefits. These will lead into the formal LEP Programme and into work. Potential for Supported Employment to run these | Outstanding | CM & KB will thought shower these in the workshops with the staff | CM & KB |
| Mentoring Programme | Essential part of LEP Programme to provide extra ‘soft skills’ support to candidates. Judith Street (Customer Services – ICS Trainer) happy to manage and run these sessions, if permitted | Outstanding | CM & KB getting quotes from providers to deliver this element – budget LSC/JCP/BHCC? | Working Together Project, Business Action on Homelessness, Rainer |
| BHCC Training & Employment Mapping | BHCC have requested that all training & employment activities across the Council be identified to share best practice. | Ongoing | KB has created a spreadsheet & questionnaire to capture this information | Gillian Marston Valerie Pearce Denise D’Souza James Dugan? |
| Work Trials | BHCC LEP Flow Chart now includes work trials element | Completed | These will kick in for each position once the candidate has been employed | JCP Contact? |
| Final Report | Engage Employment Solutions Ltd intend to produce a report detailing and capturing the experiences of the BHCC, lessons learnt etc to be launched at a Port Cullus Event | Ongoing | BHCC potentially to sponsor Would any key LSC, JCP personnel like to be involved or interviewed? | CM, KB,SR |
| Publicity | Article in BHCC’s The Channel. CM advised The Argus. The bi-annual Career Moves Event offers opportunities to publicise the LEP Programme | Ongoing | Do we need to include LEP Logo on publicity? Does BHCC PR Dept need to be involved? | Shaun Rafferty |
| Other Matters | BHCC LEP Programme needs a dedicated JCP Contact. All vacancies to appear on JCP system but JCP advisors must direct clients to Engage Forum | Outstanding | JCP to identify key local LEP contact for CM & KB | JCP Contact? |