# Brighton & Hove City Council

Meeting:	TMT

Date:		9th April 2008

Report of:	Director of Strategy and Governance

Subject:	LEP (Local Employment Partnership) Programme

- Purpose of the report

This report provides TMT with an overview of the LEP programme; its current status and recommendations to ensure its success.

- Recommendations

2.1	TMT endorsement for HR to set up a mechanism to evaluate and in discussion with management consider every vacancy from this point forward for suitability for the LEP Programme

2.2	Support from TMT to ensure every department is fully engaged with the scheme, to ensure all LEP Workshops have taken place before Engage Employment Solutions Ltd departs on the 8th July 2008

2.3	Approval by TMT of concept and budget for BHCC to commission external providers for LEP mentoring/buddying scheme

2.4	Support from TMT to provide on-site training facilities available for PET at no cost, for example Hove Town Hall

2.5	TMT to consider longer term structural arrangements to support the LEP and other into work initiatives

## Background and Approach

  - Engage Employment Solutions Ltd have been commissioned by BHCC for a minimum of six months to develop the framework for the BHCC LEP programme and deliver on the first phase, which will pilot a new process to enable local disadvantaged people to access employment within the Council. The initial consultancy work is jointly funded by the directors of S&G and Culture.

  - The programme framework has been acknowledged by Jobcentre Plus as the most accurate reflection of an LEP in the Country and once up and running will be established an example of best practice. The programme framework is detailed below (please also refer to the attached flow chart)

- All candidates to go through Assessment Process; which will test their basic skills against the basic skills required for the jobs and ask them to demonstrate why they want to work for BHCC

- Successful clients to attend PET (Pre-Employment Training), which provides accredited training on soft skills such as communication/time management and IT - the number of posts to equal the number of attendees

- Departments to interview and employ clients satisfactorily completing the PET

- Once client offered the post, BHCC will utilise the JCP Work Trial initiative; the employer and client can ‘try out’ the job and the employer does not pay a salary for the three weeks of the trial. If, after the work trial, either BHCC or the client decides not to proceed with the post, the client’s benefits are not affected; JCP will add a bonus to the client’s benefits for the period of the work trial

- Department Induction training – will vary depending on department/post

- Ongoing training for the client will be provided through Train to Gain or other relevant initiative

  - To facilitate throughput in sufficient numbers jobs will be screened in HR prior to release to see if they might be suitable for a targeted LEP placement. HR will work with managers to take a practical approach to this ensuring that key posts are not unduly delayed and that service provision is not negatively impacted.

  - The outcome of the LEP placement is to secure at least 2 years paid employment with the council. There is no time limit for the client to remain in the ring fenced post but they will be encouraged to apply for other vacancies (internal or external) through the ‘triage of support’ (line manager, supported employment agency, mentor/buddy), to open up the post for another phase of the programme. If the client remains in post after the two years, the department may be requested to identify an alternative ring fenced position

  - A mentoring programme will be established to provide support to the client during the two years on the programme. Mentors will be sought from all areas of the Council. We will consider specific training for volunteers and the payment of a small allowance to staff who undertake the role.

  - To ensure that the Programme can target those hardest to reach that are currently not ‘work ready’ there will be a supported employment placement scheme running alongside the LEP programme to provide a ‘taster’ of work to assist them to develop the right skills and motivation. These candidates will then be channeled into the Programme.

- Progress to Date

  - To date the following meetings have taken place:

| Department | Name |
| --- | --- |
| Adult Services | Denise D’Souza |
| Customer Services | Valerie Pearce |
| EBNDC | Paul Allen |
| Procurement | Claire Jones |
| Admin All Areas/Care Crew | Kieron Ives, Ken Simpson |
| Adult Services Manager | Daniel Shelley |
| Supported Employment | Maureen Pasmore |
| Equalities & Inclusion | Mary Evans, Diane Coe |
| Improvement & Organisational Development | Janice Millman, Caroline Bottrell |
| Customer Services – Institute of Customer Services Training | Judith Street |
| Housing Strategy, Homelessness & Social Inclusion | Emma Gilbert |
| Cityclean Learning Resource | Elaine Sweetman |
| Investment Manager | Simon Throp |
| Economic Development | Scott Marshall, Adam Bates |
| CYPT – Early Years East | James Dugan, Caroline Parker |
| DC Leisure | Neil Roberts |
| GMB & Unison | Mark Turner, Alex Nutson |
| Housing Needs | Nick Hibberd |
| Head of Housing Repairs | Phil Weaving |
| City Services | Gillian Marston, Rob Walker |

  - To date the following workshops have taken place:

| Department | Names |
| --- | --- |
| Customer Services | Graham Bourne, Jayne Fox, Judith Street, Paul Holloway, Chris Fossey |
| CYPT – Childrens Centre | Siobhan Hier, Caroline Parker, Celia Lamden |

The purpose of the workshops are to advise BHCC staff about the LEP Agreement, the elements of the programme and to work with them to identify jobs suitable for ring fencing and work placements.

The workshops are a key element of the LEP Project roll out, they inform and include BHCC in the LEP programme.

  - The following meetings/workshops are scheduled to take place

| Department | Name |
| --- | --- |
| Housing | Helen Furlong |
| Adult Social Care | Anne Hagan |

  - There has been a very positive response to the programme although capacity issues have been raised and not one single job has been identified to be ringfenced.

  - Phase One Timetable: At present no start date for the programme – need a minimum of 8 vacancies to be identified

4.6	Frequency of programme: Decision to be made post Phase One; however, it is suggested that this is rolled out two to three times per year.

  - Pre-employment training (PET): The LSC has awarded Working Links a 12-month ‘Skills for Jobs’ contract (ends December 2008), which is to fund PET training.     A venue needs to be sourced within the Council for this training

  - Mentoring Scheme: In house mentoring schemes are not suitable for LEP Programme; BHCC to determine if there is a funding available to bring in an external provider to set up this and then source best value. The Steering Group also highlighted the potential to link the accredited training with that for NVQ assessors, of which there is a shortage within the Council. Are there funds available to bring in an external provider to set this service up?

  - Departmental Mapping: KB is in the process of mapping the employment training and placement schemes that are currently operating in departments to ensure the LEP enhances and incorporates what is already in place and to identify:

- Good practice, recommendations and perceived barriers

- Corporate overview of activity and statistical data

- Funding being accessed and any gaps

The mapping will be complete by July 2008