## Issues Log
Engage
LEP Issues Log
Issue | Issue Type | Issue Description | History | Current Status | Impact on Project | Action | Date Resolved | Status | Comments
1 | Communication | Involvement of a large number of JCP staff | Major issues in Feb/March/April with the amount of JCP staff involvement and clarification of roles. Key contact not established. The contacts are by person rather than role, so there is difficulty in identifying who is responsible if someone is away from work. | This has been streamlined but there are still a large number of staff directly involved in communication with BHCC and information is not always shared. These include, Wayne Edmunds, Steve Benwell, Brandon Walder, Simon Poole, Dee Wishman. There is still a contact issue if someone is away - Steve Benwell to report on this. | Delay in first phase of LEP. Time consuming for Engage and BHCC in particular.
2 | Communication | JCP staff not communicating through the agreed route | JCP contacting BHCC direct and not including Engage Employment Solutions in conversations - Engage have been commissioned by BHCC to develop the framework and deliver the first phase of the LEP programme. | This has improved but is still occurring and causing frustration within BHCC and affecting the smooth delivery of the programme. For example, Simon Poole contacted Kieron Ives direct at the end of April re. AAA and Wayne Edmunds, Karen Manning (Working Links) arranged to meet with Lance Richard on 1st May 2008 to discuss the PET AAA - Engage approached Lance to be invited once they were aware. | Affects the smooth running of the programme. Information not centralised. Confusion amongst BHCC staff. Duplication of effort. Time consuming for all parties.
3 | Processes | Formal process to count a vacancy as an LEP outcome | Engage have actively sought clarification on LEP processes for last three months with JCP and no process documentation has been provided by JCP to date. | Due to lack of these, Engage have created interim measures which have been agreed with JCP. Engage are currently working with Steve Benwell and Brandon Walder to develop a local process whilst the national process is in review. Engage continue to lobby JCP for a more robust, generic and inclusive system. | Holding up the programme. Potential LEP opportunities have been lost due to lack of processes and no clarification over the means to capture. Time consuming for Engage and BHCC. BHCC officers and councillors need to see results to keep up momentum and endorse the LEP.
4 | Processes | National Call Centre | The national process states that any client from a supported employment agency (Engage Member) has to ring a national call centre to be logged as an LEP opportunity, at this point they are informed how to apply for the vacancy. There is no information available as to which Engage Member referred the client and therefore, causes an issue with tracking. Steve Benwell, Brandon Walder and Wayne Edmunds all agree that this route is not the best way of encouraging disadvantaged people to apply for posts and the system itself seems to be flawed in terms of matching the applicant to an LEP opportunity. | This is not good practice as it does not collect information on the partner organisation, which leads to tracking issues, and is not client-friendly. Another check has to be put in place to refer the client on to the PET or direct to the application and to track the individual. Dee Wishman, JCP, will need to manually follow up with BHCC or PET provider to identify whether the clients are also registered on their systems. This issue is still ongoing. | High risk of flaws in system and low effectiveness of tracking. Manual checks are time consuming and open to error.
5 | Processes | PET Provision - AAA | No AAA PET available for May as Working Links were not able to put on this training within the notice period - lack of communication of dates in advance from JCP even though these were circulated six weeks in advance. | AAA PET agreed in principal for June, details still to be agreed. | Lack of LEP take up for AAA opportunities. No LEP outcomes. Disempowering for all involved.
6 | Processes | PET Provision - General | Initially, BHCC were of the understanding that funding for PET would be coming to them direct. When followed up by Engage in February they were told that there was not any funding available for PET. Engage contacted its Forum and Sussex Careers and Rewards offered to put on the PET at no cost to BHCC. Engage were then informed by JCP that this could not go ahead as they were not approved JCP providers and the only people that could provide PET were Working Links. Working Links had won the LSC Skills for Jobs funding for Surrey and Sussex, the contract is only for 12 months and they can't take new entrants post end of July 2008; the BHCC LEP is only one client in large number trying to access this funding for PET. Working Links have also been awarded the new contract, Encouraging Employers) from July 2008, which will replace Skills for Jobs and will run for 3 years. | General PET provision for permanent vacancies still to be formalised and agreed, including timescales, regularity, capacity, content. No member of Working Links available for meeting between Working Links / JCP / Engage on 08/05/08 to discuss the processes. Meeting provisionally re-scheduled for 22/05/08. Large amount of concern that they may not agree to run regular PET programmes for BHCC because of their finite resources, this will be determined at the next meeting; there are no other approved providers so if this can't go ahead what will happen? | Time consuming and frustrating for those involved, Working Links did not attend today's meeting and did not send apologies. Concern over a single provider being responsible for all PET training, especially in light of previous experience of Jurys Inn PET programme. Not good press for LEPs. Loss of large number of potential LEP outcomes.

## Procedure
Issues Log Procedure
The Issues Log contains a summary of all issues. Use it to view open issues and to make sure that a resolution is proceeding. The Log should contain enough information to ensure that issues are not overlooked but should not be too detailed. Each issue should be represented on one line of the Issues Log.