## Instructed Action
Brighton and Hove City Council's
Local Employment Partnership Programme
Action Log
Date | Type | Key Contact | Job Title | Relevance | Description | Outstanding Action(s) | Priority 1-4 (1=High) | Assigned To | Notes | Completion Date | Status
2008-04-10 | Meeting | Anne Hagan | General Manager, Adult Social Care | LEP Programme and Mapping Introduction | Discussed potential for ringfenced jobs and workshop within department | Meeting Report, Workshop Dates, Mapping to be completed (see sheet), contact Anne's colleagues re LEP | 2 | KB | Once report received, Anne to organise workshop for her dept.
Note on B4: Meeting, Event, Phone Chat, E-mail etc
Note on L4: Ongoing, On Hold, Risk, Cancelled, Complete

## General To Do
Brighton and Hove City Council's
Local Employment Partnership Programme
To Do List
Priority 1-4 (1=High) | Title | Description | Action / Update | Notes | Assigned To | Completion Date | Status
1 | Mapping | Collate Mapping for all relevant departments | Workshops and information still to be collected. Update mapping spreadsheet. Chase relevant depts. Contact all newly identified depts - done. Mapping chase up 08/04 |  | KB
1 | Housing Workshop | Workshop on LEP - John Austin-Locke co-ordinating | Check time with John (10 not 9 as per his e-mail). Check attendence |  | KB
1 | HR Workshop | Workshop on LEP process - Ken Simpson co-ordinating | Check attendence |  | KB
1 | LEP Process | Internal and External | Create flow chart and bullets. Approval from Shaun and JCP etc. Circulate to all - Shaun, JCP, Lance, Ken etc. |  | KB
1 | AAA | Revenues and Benefits involvement in assessment day | Inform Ness Bye, Paul Holloway, Liz Morgan of Ken's response to e-mail request - Paul leading |  | KB
1 | Programme | Admin all Areas briefing document | Upload to website - awaiting details of LEP to be added. |  | KB
1 | Website | Update website with sections, photos, LEP details etc | CM Awaiting Sam at Uni's response re a student carrying out this work for free as part of their CV / coursework |  | CM/KB
1 | Mapping | Mapping | Check mapping for duplicates once all received |  | KB
1 | Meeting | Re-arrange update meeting with Ken Simpson | Postponed on 27/03 |  | KB
1 | Programme | Care Crew briefing document | Type up. Approve by Ken, Kieron and Lance. Send to JCP. Send to Engage Forum. Upload to website. |  | KB
1 | Project Management | Project Management Spreadsheet for LEP | State all actions, issues etc |  | KB
1 | Mapping | Add refugee project to mapping details?? | Not successful but discuss with Shaun re mapping |  | KB
1 | Mapping | Await mapping from Adult Social Care |  |  | KB
2 | Finance | Finance | Take over small aspects from Claire e.g. petty cash, invoices etc |  | KB
2 | Project Management | Planning tool for PET | Await infrastructure meeting with Claire |  | KB
2 | Awards | LEP Awards Brief | Create brief to submit to Claire then on to Shaun |  | KB | 2008-04-11
2 | Awards | LEP Awards | Send in Awards Nomination (deadline for receipt 02/05/08) |  | CM/KB | 2008-04-28
2 | Report - Port Cullis | Port Cullis Report | Create project sheet. Identify funding - LGA? Location, Ministers, MPs, Councillors, Officers etc |  | KB
| Report | TMT Meeting Report |  |  | KB
1 | Buddying | Set up Buddy Scheme not mentoring as lack of funding | Approval required by Shaun Rafferty. Create systems and processes
2 | Project Management | Add LEP info to monitoring spreadsheet |  |  | KB
1 | Project Management | Info on spreadsheet and to JCP regarding first phase of AAA | Chase up info on who has been shortlisted for interview and offered roles - add dates in diary (on procedure) for future months. |  | KB | 2008-04-18
1 | Project Management | Create project management tools e.g. stakeholder analysis |  |  | KB
1 | Project Management | Create spreadsheet for ringfenced job roles |  |  | KB
1 | Project Management | Create a secure document with Engage codes on |  |  | KB
2 | Report - Port Cullis | Follow up with Jonathan Shaw, Regional Minister | Contact in Research file on server. Add to Port Cullis Report spreadsheet, when created |  | KB
1 | Programme | Update internal procedure for programme. Check AAA aspect | Liaise with CM |  | KB
1 | Programme | Concern for LEP outcomes - details of NI no and DOB (amend form? Or contact Supp Empl agency?) | Liaise with CM / JCP / AAA / Shaun
2 | Partners | Rewards Policy on accompanying learners | Awaiting Paul Williams Response |  | KB
1 | PET | PET - Identify ringfenced roles |  |  | CM/KB
1 | PET | Phase One Dates |  |  | CM/KB
1 | PET | Identify training rooms | Check out Btn Town Hall Rooms |  | CM/KB
1 | Project Management | Follow up on actions from meetings | Meetings spreadsheet |  |  | Weekly
2 | Report | Two weekly meeting reports to Shaun then Alex for approval before circulating to Scott
3 | PR | PR opportunities for LEP | City News, Report, The Argus
3 | Project Management | Include Unions in LEP procedure

## To Purchase
Brighton and Hove City Council's
Local Employment Partnership Programme
Purchase Log
Item | Amount | For Whom | Details | Purchase By Date | Status | Cost