# Brighton and Hove City Council

Local Employment Partnership (LEP) Programme

Project Brief

January to July 2008

- Background

Brighton & Hove City Council has contracted the services of Engage Employment Solutions Ltd, for a minimum of six months, to assist in the development and delivery of their LEP programme.

The work plan will be formally reviewed half way through the contract to ensure the direction of the work is compatible with the overall LEP strategy within the Council.

- Project Aim

The overarching aim of this project is to assist the Council to employ a more diverse workforce reflective of the local labour market.

This will be achieved through the development of viable employment route ways within the Council for local residents from under-represented groups, by providing the right skills and qualifications for them to source employment within local economy.

- Audience

This project is primarily directed towards clients from the following under-represented groups:

  - Lone Parents

  - Long term unemployed

  - Residents over 50

  - Residents currently claiming Health related Benefits (Pathways)

  - People with disabilities

  - People from deprived areas

- Project Delivery

Initially the focus will be on assessing the recruitment and retention needs of the following departments, as identified by the Assistant Director Head of Human Resources, Shaun Rafferty, as currently experiencing recruitment issues or having employment opportunities’:

- Benefits Department

- Adult Social Care

- Horticulture

- Children’s Centres

- Construction

  - One-to-one meetings will take place with the appropriate department head to:

- Evaluate the tasks required to deliver the work of the department

- Evaluate the current job roles, as matched against those tasks

- Identify hard to fill job roles

- Identify where flexible working practices can be introduced (especially relevant for some parents and clients with health disabilities)

  - The Learning & Skills Council (LSC) have made a national commitment to provide the funding to support the necessary pre-employment training required to up-skill the clients before they can begin this programme. This pre-employment training programme will be designed to reflect the skills needs of the specified departments, as researched in the primary one to one meetings with the department heads.

  - Certain agreed job roles will be ring fenced for this programme for an unspecified time period. Where possible these roles will reflect the employment needs of the local economy to ensure clients are being trained up to fill employment gaps. This process will rely heavily on accurate labour market intelligence.

  - The job roles will be fixed for a two year period for each client; at the end of the two year period the client will be encouraged and assisted to source employment either elsewhere within the Council or the local economy. The ringfenced position can then be filled by another client.

  - Job search and employment support from the referral agencies (Engage Brighton & Hove Forum member) will continue for the two year period to ensure the client is supported to maintain employment or seek employment elsewhere. Evidence suggests that two years is the average time period to re-socialise clients and make their employment sustainable.

  - During the client’s life cycle on the programme clients will be trained in appropriate qualifications where possible, utilising initiatives such as Train to Gain. This guarantees that whilst the client gains industry recognised qualifications and develops a career path they will be attractive to local businesses. This also assists the Learning and Skills Council to deliver upon its Train to Gain programme in an organised manner.

  - A mechanism for recording the client’s journey through this programme is fundamental to manage the process effectively.

In conclusion, this part of the programme enables the Council to be a supported route way to provide the local economy with a skilled labour force.

- Funding

As mentioned in paragraph 4b the LSC will be providing the funding to deliver the pre-employment training programmes. The pre-employment training programmes will be no longer than two weeks long.

Subsequently the clients will be put on the Jobcentre Plus (JCP) Work Trials programme, which will last up to 15 working days. The client remains on benefits during this time, which allows both the client and the Council to ensure that the job role is suitable before an official salary commences.

Other funding to support the pre-employment programme could come from the Engage members, who have contracts with JCP, such as Pathways, to support these clients groups into employment. Further research into this will take place once the job roles have been identified and ring fenced for the programme.

- Additional Initiatives

During this delivery of this programme it is feasible to operate the following additional services:

- Staff Buddy Scheme – existing staff within the Council are given the opportunity to buddy the clients coming through this programme as part of their personal development and the Council’s overall commitment to corporate social responsibility, as briefly outlined in the Leader Group Charter (www.brightonbranch.co.uk/leader)

- Placement Scheme – preliminary identification of departments most reflective of the local economy, such as administration and hospitality. Evaluation of any positions suitable for work placements, positions where existing employees are on long term sick, maternity leave etc

- Reporting Structure

Project Sponsor – Alex Bailey, Director of Strategy & Governance, BHCC

Project Lead – Shaun Rafferty, Assistant Director, Head of Human Resources

Project Delivery – Claire Mitchell, Director of Engage Employment Solutions Ltd, reporting into Shaun Rafferty

Project Delivery – Karen Barford, Consultant of Engage Employment Solutions Ltd, reporting into Claire Mitchell

8. Further Opportunities

There is the opportunity to promote this scheme on the Engage Employment Solutions Ltd website, which experiences high volumes of traffic from all sectors (employers, public, community and voluntary)

The scheme could also be developed to promote the Council to school leavers, working in partnership with Lawton Ware, local recruitment agencies and the Education Business Partnership.