## Sheet1
Activity | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01
Phase 1 (Set Up)
Logo
Write brief for artwork | bar: 2008-07-01
Meet with designers | bar: 2008-07-01
Agree options with task group | bar: 2008-07-01
Present to full partnerhip | bar: 2008-07-01
Website
Write brief for website | bar: 2008-08-01
assess options for hosting | bar: 2008-07-01 to 2008-08-01
create site | bar: 2008-08-01 to 2008-12-01
Launch site | bar: 2009-01-01
Produce clear aims and project message
Write simple project breakdown | bar: 2008-07-01 to 2008-08-01
Produce clear literature on how to get involved | bar: 2008-08-01 to 2008-10-01
Present to full partnerhip | bar: 2008-11-01
Launch Event | bar: 2009-01-01
Book venue | bar: 2008-07-01 to 2008-09-01
Invite partners/guests | bar: 2008-08-01 to 2008-12-01
Run Event | bar: 2009-01-01
Phase 2 (Publicity)
Pre event publicity
Editorial in local press (Argus) | bar: 2008-11-01 to 2009-01-01
Editorial in business Forum web | bar: 2008-11-01 to 2009-01-01
Editorial in business mags | bar: 2008-11-01 to 2009-01-01
Editorial in Hove Business News | bar: 2008-11-01 to 2009-01-01
City Council website | bar: 2008-11-01 to 2009-01-01
City College Website | bar: 2008-11-01 to 2009-01-01
Engage Website | bar: 2008-11-01 to 2009-01-01
Other | bar: 2008-11-01 to 2009-01-01
Produce printed promo literature | bar: 2008-09-01 to 2008-10-01
Mail drop promo literature | bar: 2008-09-01; 2009-01-01
Access social blogging/marketing sites
Engage Business Champions
Phase 3 (Courses + Post Launch publicity)
Run Courses | bar: 2009-02-01 to 2009-08-01
Continued positive stories in press and media | bar: 2009-02-01; 2009-04-01; 2009-06-01; 2009-08-01
Biz Forum Website | bar: 2009-02-01; 2009-04-01; 2009-06-01; 2009-08-01
City College Website | bar: 2009-02-01; 2009-04-01; 2009-06-01; 2009-08-01
Hove Business News | bar: 2009-03-01; 2009-05-01
Editorial in business press | bar: 2009-02-01; 2009-04-01; 2009-06-01; 2009-08-01
etc other | bar: 2009-02-01; 2009-04-01; 2009-06-01; 2009-08-01
Phase 4 (Review + Future Funding) | bar: 2009-08-01
Course Assessments | bar: 2009-08-01
PR Assessment | bar: 2009-06-01 to 2009-08-01
Apply for funding for 09/10