SOLD (Sector Originated Learning & Delivery)

Steering Group

Terms of Reference

June 2007

##### Mission of the Group

The effectiveness and success of the project depends on strong partnership working and a high level of consultation with all partners and stakeholders. The steering group will work in partnership to achieve the two objectives of the project which are:

1. To collate existing, and undertake additional, research into the exact training needs of the retail/tourism sectors of the City of Brighton & Hove

2. Determine the actions required to address the needs and produce a report and action plan from these findings.

Actions required from the Steering Group re Key Stages & Milestones

> Discuss research findings

> Determine what courses need to be developed / delivered and by whom

> Develop School to Work initiative

> Ensure discussions with Awarding Bodies if applicable

> Develop marketing plan

> Ensure courses are marketed through promotional activities

> Employers are asked to sign up to training agreements

> Training courses delivered for both sectors

##### > Monitor the programme and record impact on business

> Members to be available to assist the Project Co-ordinator

> Responsible for signposting employers to training not provided by SOLD

> Responsible for monitoring the budget

Membership

Form a Steering Group which will comprise of:

- 2 CoVE representatives (1 from Retail and 1 from Tourism)

- 2 Employers

- 1 Sussex Skills for Productivity Alliance representative

- 1 Delivery partners (Rewards, BHTA, VT Training) representative

- 1 Sussex Enterprise representative

- 1 Engage representative

- 2 City College Brighton and Hove representatives (Researcher and Project Co-ordinator)

- 1 Brighton and Hove Business Forum representative

- 1 Brighton and Hove Council representative

##### Accountability

The group through the Project Co-ordinator will provide bi-monthly reports to Cheryl Finella

Economic Development Lead Officer, Economic Development, Brighton & Hove City Council

# Organisation of meetings

Role of Chair to be divided between nominated employers such as;

Kevin Berry, Old Ship Hotel

Additional employers accepted by the group as beneficial to the project

6-weekly meetings

Agenda to be issued by Project Administrator with contributions welcome from group members

#### Signed Agreement

#### This is to confirm that as a member of the SOLD Steering Group I confirm my acceptance and commitment to the above mentioned terms of reference

Signed:	……………………………………………………………………………………

Name:………………………………………………………………………………………

Position:……………………………………………………………………………………

Organisation:………………………………………………………………………………

Date:………………………………………………………………………...