| Task / Activity | Priority |  |  | What tasks need to be completed to achieve this? | Who? |  |  | Resources needed? |  | Due date? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Awareness Campaign |  |  |  |  |  |  |  |  |  |  |
| To ensure a strong level awareness of the Project with relevant local employers | HIGH |  |  | - Employer Sign Up - Employer Meetings - Employer E-list | CM CM CM |  |  | - CM’s Time - F.O.C Venues across the City - CM’s web services |  | Ongoing |
| Network of Employers |  |  |  |  |  |  |  |  |  |  |
| Set up an employer network to work on this Project | HIGH |  |  | - Select appropriate local employers passionate about training and learning - Create Employer Pack detailing Project and employer requirements - Introductory Meetiny | CM JR CM & JA |  |  | - CM’s Time - Employer Pack - Venue - Presentation |  | April 2009 June 2009 |
| Work Placement Mentors within Businesses |  |  |  |  |  |  |  |  |  |  |
| Identify mentors within businesses to take responsibility for placementees | MED |  |  | - Explain the requirement for mentors - Create paperwork and process to select and support mentors with employer involvement - Identify mentors within employer network - Sign them up to programme | CM CM CM CM |  | - CM’s Time - Mentor Packs - Employers Input |  | June 2010 |  |
| Work Placement Tool Kit |  |  |  |  |  |  |  |  |  |  |
| Tool Kit for both Employers and work placement candidates outlining all elements of the process and structure | MED |  |  | - Creation of process using a combination of existing Routeway paperwork and EES paperwork - Creation of templates capturing each stage of the process; i.e. work placement description, employer contract - Employer input into above two tasks - Comparison with French processes and paperwork to ensure best information is used - Finalised Templates to be shared by all interested parties and stakeholders such as People’s First | CM CM Employers CM, JA ALL |  | - CM’s Time CM Employer’s Time CT, JA, CM ALL |  | April 2010 |  |
| Good Practice Charter |  |  |  |  |  |  |  |  |  |  |
| Charter of Good Practise between the French and British Partners outlining the Project and it’s intentions | LOW |  |  | - Charlie Turner and French colleague have already started the Charter; CM to view - CM to present to employers for their input - Employers to Sign it | CT CM CM Employers |  | - CT to email it - CM’s Time - Employer’s Time |  | Nov 2010 |  |
| Communication Protocol for Employers |  |  |  |  |  |  |  |  |  |  |
| Creation of a communication method designed to keep employers up-to date with all relevant Project information | MED |  |  | - E-List - Employer’s input into most suitable format and frequency - Newsletter; JA and KB to inform CM of all relevant information? | CM Employers JA, KB, CM |  | - CM’s Time - JA & KB’s Time |  | Post 20.01.10 Employer’s Meeting |  |
| Work Placement Tool Kit |  |  |  |  |  |  |  |  |  |  |
| Tool Kit for both Employers and work placement candidates outlining all elements of the process and structure | MED |  |  | - Creation of process using a combination of existing Routeway paperwork and EES paperwork - Creation of templates capturing each stage of the process; i.e. work placement description, employer contract - Employer input into above two tasks - Comparison with French processes and paperwork to ensure best information is used - Finalised Templates to be shared by all interested parties and stakeholders such as People’s First | CM CM Employers CM, JA ALL |  | - CM’s Time CM Employer’s Time CT, JA, CM ALL |  | April 2010 |  |
| Good Practice Charter |  |  |  |  |  |  |  |  |  |  |
| Charter of Good Practise between the French and British Partners outlining the Project and it’s intentions | LOW |  |  | - Charlie Turner and French colleague have already started the Charter; CM to view - CM to present to employers for their input - Employers to Sign it | CT CM CM Employers |  | - CT to email it - CM’s Time - Employer’s Time |  | Nov 2010 |  |
| Communication Protocol for Employers |  |  |  |  |  |  |  |  |  |  |
| Creation of a communication method designed to keep employers up-to date with all relevant Project information | MED |  |  | - E-List - Employer’s input into most suitable format and frequency - Newsletter; JA and KB to inform CM of all relevant information? | CM Employers JA, KB, CM |  | - CM’s Time - JA & KB’s Time |  | Post 20.01.10 Employer’s Meeting |  |
| Evaluation of Project by Employers |  |  |  |  |  |  |  |  |  |  |
| Feedback on employer’s experience of the Project to improve future work involving employers |  | LOW | - Meeting to be arranged towards end of Project - Creation of an Evaluation Template to be used - Writing a Report on Findings - Presenting to ALL interested parties |  |  | CM CM CM CT, KB | CM’s Time CM’s Time CM’s Time CT, KB Commitment |  | August 2011 |  |