VIP Interreg UK Delivery Plan

| Action | Indicator | Activity | When | Key partners | Lead partner | Outputs /Outcomes |
| --- | --- | --- | --- | --- | --- | --- |
| - Mainline 1: adapted work |  |  |  |  |  |  |
| Mainline 1: operational goal 1: - Awareness campaigns and training of the French and British management staff | Production of publicity materials, booklets and manuals | Develop a plan for the production of a defined set of educational and publicity materials to specified target audiences | Feb 2010 | Nourish, Care Co-ops & engage | Nourish | Increased awareness of French and British management staff in relation to the newly developed harmonised system of support to beneficiaries in assessing mainstream work and learning opportunities |
| Mainline 1: operational goal 2: - To identify and enhance the competences of the workers with disabilities working in the French and British specialised organizations from the existing frames of reference and to develop and build on this | Establish a framework of groups to promote exchange of ideas and sharing of good practice | Map the elements of training and support offered to beneficiaries. Explore common areas of practice and develop a harmonised model of good practice |  | Nourish, Care Co-ops | Nourish | Disabled workers identified and supported to enhance levels of competences |
| Mainline 1: operational goal 3 - To develop plans of continuous training adapted to the needs, expectations of the beneficiaries in accordance with the economic changes | The ongoing development of an effective model of delivery with a focus on continues shared improvements | An ongoing development process of continues improvements based on shared learning |  | Nourish, Care Co-ops | Nourish | Overall training plan implemented and adapted to the expectations of beneficiaries that is responsive to economic conditions |
| Mainline 1: operational goal 4: - To analyze the conditions and opportunities for transfer of the know-how in the mainstream work environment | Engagement with employers in taking a lead role in the development of good practice. | Building a platform of employer involvement in the development of specific support structures that emblem beneficiaries to be supported in open employment |  | Nourish, Care Co-ops & engage | Nourish | To build a evidence basses platform of practice that supports beneficiaries to work and learn in mainstream settings |
| Mainline 2: operational goal 1: - To inform and make awareness campaigns towards the French and British firms in the framework of a common communication plan | Grater engagement with employers | Development and support of a network of employers to participate in the development of effective support services |  | Engage Care Co-ops and nourish | Engage | To have delivered an awareness chaplain in France and Brittan aimed at Business to support the development of good practice in beneficiaries accessing mainstream opportunities |
| Mainline 2: operational goal 2: - To identify a network of partner firms and to set up the necessary conditions for its development by integrating training actions intended for the tutors inside the firm | To identify tutors/assess/mentors within business to participate in the project | To implement a structure approach to the engagement and support of tutors/assessors/mentors in firms to engage in the project as part of their professional development and assist in the development of the project |  | Nourish & Engage | Engage | To develop a structure for the support of a cross border next work of business that aims to integrate training available to tutors within businesses |
| Mainline 2: operational goal 3: - To organize and lead a secured gateway of professional activities towards the main stream work environment in partnership with professional organizations | Partnership agreements with business including a commitment to develop good practice and support systems for grater access to mainstream employment. | To devolve a tool kit of support that enables an individual to move towards mainstream learning employment in partnership with relevant professional organisations like the sector skills council and national awarding body |  | Care Co-ops, Engage & Nourish | Care Co-ops | To work collaboratively with professional organisations To make strong linkage with wider strategic policy objectives |
| To create steering committees | To provide advice and guidance to operational staff within the cross-border work teams | To hold overall governance for the process of recognition and validation of the experience and professional integration into mainstream and suitable environment. |  | Care Co-ops, Engage, Nourish & Reps from Business | Care Co-ops | To develop a harmonised cross border structure that maps and develops good practice in the support of beneficiaries in assessing mainstream work and learning opportunities |
| The establishment of a network of the partners institutions and drafting of a charter of good practices. | Mapping of processes in supporting beneficiaries to access mainstream opportunities | The agreeing of a charter of good practice for the progression of beneficiaries in to mainstream learning and employment opportunities |  | Engage nourish & Care Co-ops | Engage | To convene a next work of business and develop a charter of good practice with then |
| The definition and organization of experimental areas (development of a methodological cross-border scorecard). | Identification, development and piloting of new approaches to supporting beneficiaries to access mainstream opportunities. | Building on the Individual Placement & Support (IPS) model develop evidence basses approaches that work in the due locations of France and the UK |  | Nourish & Care Co-ops | Nourish | Actively participate in the deployment of pilots experimental projects using an evidence based approach in developing as shared cross border methodological frame work |
| The final validation of the target groups tests of English and French recipients | Undertake negotiations with national awarding body and strategic institutions in the harmonisation of the validation process | To implement a harmonised system of validation and recognition of achievement. |  | Care Co-ops Nourish | Care Co-ops | To establish an agreed harmonised validation system between French and English partners |
| The clear positioning of outside suppliers in the global scheme of operations (development tools for internal and external communication engineering and evaluation). | Commissioning of an external consultant for the development of an IT platform of communication engineering and evaluation | Development of an CIT communication and training platform |  | Nourish & Care Co-ops |  | The appointment of an outside consultant for the development of ICT platform |
| - Organizing arrangements for the exchange of technicians and technical study visits. | Identification of technicians for study visits | To undertake a sires of technical study visits |  | Care Co-ops, Nourish | Care Co-ops | Undertake a planed number of study visits for technical staff |
| - Establishing awareness plan and business information. | Establish the information needs of the business community in being provided information about this project | To implement an information strategy for the engagement and retention of business in the development of this project. |  | Engage, Nourish & Care Co-ops | Engage | Putting in place a package of support for businesses to fully engage in the development and management of this project |
| The creation of a cross-border training package: composed of the following tools: |  |  |  |  |  |  |
| Tool Kit facilitating beneficiaries accessing mainstream opportunities including the following:- - training and communication tool - portfolio of skills - inter-institutions placements - methodology for the establishment of a process of skill recognition -drafting of a charter for implementation -development of reference frames of formation and evaluation - drawing up plans for training pilots (credit) focus on skills enabling workers to move towards professional degrees below V validated by both English and French partners the creation of a cross-border collaborative work platform to enable the partners to capitalize and to spread all the contents realised in the framework of the project. | The establishment of a cross boarder working group with responsibility for the development of the tool kit | The development and implementation of the harmonised cross border Tool Kit |  | Nourish, Engage & Care Co-ops |  | To increased mobility : through increasing grater access to mainstream work and learning opportunities To create a dynamic individual, less dependent on specialist institutional support |
| The setting up of a study visit plan: | The organization of a cross border programme of study visits (in priority: green spaces, cooking and catering, jobs linked to the sustainable development). | To implement a programme of exchanges of workers with disabilities managed by leaders resulting in grater awareness |  | Care Co-ops & Nourish | Care Co-ops | To plan and implement a study visit programme with French partners |
| Create a structure for admiration and technical support which interfaces with the lead French partner | Negotiate the different elements of the new structure with Lead French partner. Undertake training in the operation of the new system. Provide training advise and support to UK partners | Implement new system and receive retunes information for processing |  | Care Co-ops | Care Co-ops | Manage the overall system of reporting on the UK side |
| Below are not outcomes that we are needing to reach but are overall objectives of the programme |  |  |  |  |  |  |
| - In terms of outcomes, these are the aims: |  |  |  |  |  |  |
| - Secure Professional careers; |  |  |  |  |  |  |
| - For increased mobility : throughout the protected sector and from the sheltered sector to the mainstream work environment; |  |  |  |  |  |  |
| - To create a dynamic individual, crossing away from institutional; |  |  |  |  |  |  |
| - A renewed respect for workers with disabilities and to improve their self-esteem. |  |  |  |  |  |  |