## Sheet1
EBH04 Gannt Chart |  | Month
Ref | Activity | July | August | Sept | Oct | Nov | Dec
1.1 | 1-2-1 Meeting with Supported Employment Agencies
1.2 | Develop Engage Type network or develop existing 'Pathways to Work' Forum | bar: Month Sept
1.3 | Terms of Reference for Engage WS | bar: Month August to Month Oct
1.4 | Set up EE Forum to support Engage WS | bar: Month Sept to Month Dec
1.5 | Develop potential sustainability options for Engage WS | bar: Month Nov to Month Dec
2.1 | Project Manage development of LEADER Brighton & Hove | bar: Month July to Month Oct
2.2 | Promote and co-ordinate membership to approp. Employers and public sector bodies | bar: Month July to Month Oct