## July
Number | Date | Meeting/Call/Activity | Organisation | Meeting Contact | Action | Outcome
1 | 29.6.07 | M | LEADER Group | Kirsty M, Sam, Linda | Need to contact Gill Whensley from CIPD. Put ideas for TOR forward. Organise meeting venue for 10.8 meeting,
1 | 4.7.07 | C | Steps to Work | Jackie Davey | Introduced Engage WS & explained was interested in expanding the Steps to Work membership etc. She is interested in this, meeting on the 26.07.07
1 | 4.7.07 | C | JCP Welfare to Work | Angie Elliot Dickson | Introduced Engage WS & explained was looking for a strategic group to report into and to pass information from. She invited me to the meeting on the 19.7 to discuss this point with the members.
1 | 4.7.07 | C | Private Consultant? | Rolland Higgins | Discussion on his directory, he will send me a copy of it. It is not finished yet, we wants me to check it
1 | 4.7.07 | A | Terms of Reference |  | Amended to reflect WS
1 | 4.7.07 | A | Information Sheet |  | Amended to reflect WS
1 | 16.7.07 | C | WSCC | John Hoyland | He is responsible for sustainability programme in schools on a project called Engauge - he wanted to check what I was doing to see if it was the same thing! Thinks there might be synergy in the future….
1 | 16.7.07 | C | WSCC | Ron Crank | Finally caught up, he is very interested to hear more and help to isolate a strategic group. Meeting for lunch on the 20.7.07
1 | 16.07.07 | C | WSCC | Phillip Coleman | Informed him that someone from JCP had suggested I present to the Public Service Board about Engage WS. He explained that Becca Randall was doing a presentation on West Sussex Works and that I should speak to her. Explained she was Kisrty's manager and we were both aware of each other. He suggested I speak to Berry Bonner Le Fur and Aiden Petit to explain what I was doing and Paul Mcgloin.
1 | 18.7.07 | C | WSCC | Becca Randall | She called me back, informed me Ron had had a heart attack and therefore we would not be meeting. She suggested that the Regional Skills Alliance might be the strategic body and said Ron or his manager, Kieran Stigant, would be best to advise. She also suggested I spoke to Caraline Woods from the Economic Partnership.
1 | 19.7.07 | M | JCP Welfare to Work | Angie Elliot Dickson | Met with Angie to discuss Engage WS, she is keen to support it. Informed me who was best within her staff to sit on it etc.
1 | 19.7.07 | M | JCP Welfare to Work | Angie Elliot Dickson | Mainly JCP staff in attendance although did meet Jane Taylor - Becca Randall's job share and the Head of the Volunteer Bureau who should call me to talk. All were very interested in Engage WS and want me to attend the next meeting. Explained this would be down to time, as they will be asking Kirsty M to do a presentation on West Sussex works she potentially could give an update of Engage WS. JCP have just completed a map of all of their providers in WS, will email this to me.
1 | 19.7.07 | M | Impact Workability | David Ambler | Project info visit, David wanted to know what Engage WS had to offer, explained what Engage B&H was and said it would depend what the members wanted the group to look like but the over all aim would be about empowering agencies to sign up more businesses and therefore get more people into work. He was concerned about the competitive nature of other agencies in the area.
1 | 24.07.07 | M | Business Edge | Steve Cotterill | Discussion on LEADER, he wants some information to give editorial coverage
1 | 26.07.07 | C | Economic Partnership | Alastair Smith | Alistair was involved in DEB in the beginning, he is confused by DEB, Pathways, West Sussex Works. Explained I would be providing clarity. He said there is a large scale of employers across West Sussex. Found local events work more effectively. Simon Warburton was trying to do EE for Economic Partnership and tried to impart his skills on but he left some time ago and went up North.3 Districts split - Northern, Coastal, South Downs. 7 Districts in WS.They have a Northern Group of ED Officers (3) - 4 people - more around Gatwick Diamond. Coastal Group has a lot of ED officers. They have a e-newsletter and a magazine for their business, asked if I could write something for this and present to businesses he will let me write for e-newsletter. Wholly funded by public sector to take economic strategic view of County, they have a list of the business associations across the County. Chichester College has business breakfasts, 60/70 businesses. Explained about PET packages we could offer - Caraline Wood has been working on this at Gatwick - skills centre pilot been running for 18 months but employers are reticent because they have to pay. Asked him to let me know everytime a new business comes to WS and needs staff as we can organise the PET.
1 | 26.07.07 | M | The Argus | James Lancaster | The Argus is county-wide and therefore can have a West Sussex Engage Group Placement League and coverage.
1 | 26.07.07 | C | SEEDA | Chris Chapman | Got referred to Chris via Alistair Smith, explained what Engage B&H did and what I wanted to do in West Sussex. He has some employers in mind - directed him to the website. He is the investment development manager.
1 | 26.07.07 | C | Impact Workability | Maxine Thomas | She wants to meet me face to face to understand Engage, meeting 1st August at 9am at the Brighthelm
| Total | 0

## Aug
Number | Date | Meeting/Call/Activity | Organisation | Meeting Contact | Action | Outcome
1 | 01.08.07 | M | Impact Workability | Maxine Thomas | She has concerns about the competitive nature in this sector, she wanted a brief of the intentions of Engage WS. Sent her this, the TOR and the Project Info sheet. She will discuss Engage WS with the Steps into Work Group.
1 | 02.08.07 | M | Ranstad | Joannah Griffin | She is keen to work with Engage WS and provide assistance where ever possible. They want to expand their activities in this area.
1 | 3.08.07 | C | Sussex Probation | Gary Woods | Meeting him on the 13.08.07 to discuss Engage WS
1 | 03.08.07 | C | EBBS | Lorraine Bells | Made meeting for the 9.08.07
1 | 03.08.07 | C | EOPPS | Julie Buckingham | Meeting for the 7.08.09
1 | 03.08.07 | C | Rewards | Paul Williams | Meeting for the 08.08.07
1 | 03.08.07 | C | Worthing Mind | Jenny James | Meeting on the 17.08.07
1 | 2007-08-06 | C | RBLI | Traci Edwards Vine | Meeting on 20.08.07 with Melissa who has worked in WS for a long time
1 | 2007-08-06 | C | Shaw Trust | Steve Jones | Covers Surrey & Sussex - meeting on 20th August 07
1 | 2007-08-07 | C | Sussex Deaf | Teena White | Meeting on 14.08.07
1 | 2007-08-07 | C | Kennedy Scott | Helen Lang | Meeting 17.08.07
1 | 2007-08-07 | M | EOPPS | Julie Buckingham | Project Info meeting - suggested Mencap as members will send details. Got resources to share but not funds.
1 | 2007-08-07 | C | WSCC | Helen Loe | Going to meet with her and her boss on the 29th August 07
1 | 2007-08-08 | M | Rewards | Paul Williams | Signed WS TOR etc - will fill in the EE Directory
1 | 2007-08-09 | M | EBBS | Lorraine Bells | She is not currently working in this area but is keen to be on the Directory and offer services
1 | 2007-08-10 | M | LEADER | Hilary W, Kirsty M, Sam R, Linda B | Discussion on development of LEADER, TOR, Hilary's experiences etc
1 | 2007-08-10 | M | DEB | Kirsty Mackenzie | Quick catch up, discussion on future chair of West Sussex Engage. Could be David Cane, which would fit well with his role in West Sussex Works. She will broach David and come back to me. Discussion on my workshop at the DEB Dissemination Event,need to determine subject by end of August.
1 | 2007-08-13 | C | Steps into Work | Jackie Davey | Rescheduled meeting to 17.08.07
1 | 2007-08-14 | M | Sussex Deaf | Teena Whyte | Project Info Meeting - she suggested some other organisations and will talk to them before passing on their details. They have a good meeting room but usually there is a charge, she will investigate on whether we can have it for free.
1 | 2007-08-15 | M | Kennedy Scott | Helen Lang | Project Info Meeting - she will forward the details of some other organisations she thinks might be relevent.
1 | 2007-08-17 | M | Pathways to Work | Jackie Davey | Meeting, am allowed to go and present to Steering Group in October. She doesn’t think the current partners will welcome new partners unless they have something to offer. She seemed pleased that David Cane could potentially be running the Group. Sending her the TOR and EE Directory for WS.
1 | 2007-08-20 | C | Everyday Recruitment/Next Steps | Irene | They were recommended by KS, they have heard of Engage and are keen to meet up and become part of it.
1 | 2007-08-20 | M | Shaw Trust | Steve Jones | Project info meeting, he is really keen to be a member of this Group and really gets the partnership goal. He will talk to his manager about this as he operates in Brighton and Hove.
1 | 2007-08-23 | M | RBLI | Mellissa Hamilton | Project info meeting, Traci Edwards Vine was there to explain the B&H Services. Mellissa was keen for there to be a website like the current DEB one advertising jobs with positive companies.
1 | 2007-08-28 | M | WSCC | Ron Crank | Their emphasis is on the coastal areas of deprivation, Selsey, Bognor R, Shoreham and Littlehampton.He regularly meets with Lynne Connolly, Lynda Jones, Mike Burgess to discuss County strategy. He is involved in setting up a Sussex Employers Consortium with JCP and LSC funding. There are 7 districts in WS, each has its own EDO which in turn have their own employer groups! I could target both the WS Econ Partnership Newsletter & Business Edge for publicity. He has taken the business plan to get a real understanding of what Engage is about and he will see how best it fits into WS.
1 | 2007-08-29 | M | WSCC | Helen Loe | Discussion on the change of the HR function, being restructured for the 1st Oct, she is not sure if she will be around in her position. Which is to manage the Manpower contract, which is the s/a at the BHCC Carlysle vendor set up. Manpower are going to provide a recruitment consultant and admin support to West Sussex Works. She signed up to Engage WS
1 | 2007-08-29 | M | Everyday Recruitment/Next Steps | Barry Vaughan | They are the only recruitment company in the UK with a Next Step Contract, they are very socially minded. Asked if Engage WS members could join in their training as & when it is on - Barry will check. His colleague, Irene, is checking whether Connexions have large enough premises to host Engage meetings. They joined Engage WS
1 | 2007-08-29 | M | Worthing Mind | Jenny James | Project Info Meeting, they are part of Pathways to Work. She wants training on the business case for EE as she has no commercial background.She will talk to her manager about signing up to Engage WS
1 | 2007-08-30 | M | Rainer | Leigh Flack | She has experienced problems with partnership working in WS, she has presented to Pathway to Work member organisations a couple of times but they simply don't seem to want to work with Rainer and pass on leads, which is frustrating. It is hoped Engage WS will bring an end to this as the New Beginnings Project ends in March 2008. She is going to refer on a couple of people who would be useful contacts to present at meetings.
| Total | 0

## Sept
Number | Date | Meeting/Call/Activity | Organisation | Meeting Contact | Action | Outcome
1 | 4.09.07 | M | University of Brighton | Sam Rhodes | Went through content of LEADER workshop, he will make some changes and come back to me. He will check with Kirsty as to when we need to be there.
1 | 05.09.07 | M | VT Careers Management | Ed White | Ed co-ordinates Asphalaya, Sussex Training and Central Sussex College on the e2e contract. Project info visit, he will take the Engage WS papers to his manager to see about joining.
1 | 07.09.07 | C | WSCC | Chris Hodgeson | Called me from meeting from with Ron Crank to ask how he can assist Engage WS, he has the business plan. Skills Escalator is an LSC initiative suggested to AIF board which has been amalgamated with Learn to Earn - tender is out for 7 months of consultancy results in next week - similar objective to Engage - looking at why the hard to reach groups aren't accessing employment. He will send documents for me to review, said to come back to me if can't find anyone.
1 | 13.09.07 | C | CIPD | Gill Whensley | Finally afer much to'ing and fro'ing she got my emails - she cant make the LEADER workshop but we will meet on the 25th Sept ar 4pm to discuss.
1 | 2007-09-17 | M | LEADER/Marketing Gym | Dee Blick, K Mackenzie, S Rhodes | Discussion on marketing for LEADER & DEB Workshop content. Putting something together for the Steering Group
1 | 2007-09-18 | M | Southdowns Housing | Sue Goodwin | Engage Project Meeting, she is going to give it a try but is sceptical about the competition. She will send me the TOR once she has read it.
1 | 2007-09-18 | A | Leader Steering Group Statement |  | Put together draft Steering Group Statement
1 | 2007-09-19 | C | Scope | Jan Foster | Finally tied her down to a meeting on the 5th October
1 | 2007-09-19 | A | Leader Steering Group Statement |  | PowerPoint presentation and questionnaire for Leader Workshop (1/2 day)
1 | 2007-09-21 | M | DEB Grand Finale Event | Leader Workshop | Only 1 employer attended - Martin Searle, who signed up to be part of Leader.
1 | 2007-09-20 | A | The Argus | Stephen Lowe | Spoke to him about possibility of West Sussex Argus Jobs Fair - he seemed interested and asked me to call him
1 | 2007-09-25 | M | CIPD | Gill Whensley | She is very keen to be involved with Leader and will come to the 19th Oct meeting.
1 | 2007-09-26 | C | Martin Searle | Fiona Martin | She's glad Gill is involved and will think about others that could be involved
1 | 2007-09-26 | C | Hub 100 | Phil Green | He is very interested in the concept, can't make the 19th Oct but will send a delegate. I am sending him all the information.
1 | 2007-09-27 | M | DEB | Kirsty M/David Cain | Discussion over his taking over the Chair of Engage WS and what that entails. Set dates for future meetings and planning meetings
1 | 2007-09-27 | M | Working Links | Oliver Green | He will be the lead for Working Links in WS - sent him the invite for the first meeting
1 | 2007-09-27 | C | RBLI | Traci Edwards Vine | She is happy to come to the first Engage WS meeting to give a presentation on her experiences of Engage Brighton & Hove
1 | 2007-09-27 | A | Leader |  | Sent invitation to a number of employers for 19/10/07 Workshop
18 | Total | 0

## Oct
Number | Date | Meeting/Call/Activity | Organisation | Meeting Contact | Action | Outcome
1 | 2007-10-01 | A | Hotel du Vin | Lora Strizic | She will come to Leader Workshop on 19th Oct
1 | 2007-10-02 | A | Martin Searle | Fiona Martin | She wanted to know if she should suggest some other employers, I said I think we have enough.
1 | 2007-10-02 | A | Telegen Uk | Sally Hall | She confirmed she is attending the Leader Workshop on 19th Oct
1 | 2007-10-03 | A | Randstad | Joannah Griffin | She confirmed she is attending the Leader Workshop on 19th Oct
1 | 2007-10-03 | A | Sussex Police | Angela Packerbusch | She was concerned that she heard about this meeting from her director and she'd already arranged to meet with me on the 15th Oct - explained I wasn’t responsible for sending that partic invite. She will determine from our meeting as to whether she wants to attend Leader
1 | 2007-10-04 | A | DMH Stallard | Sandie Whitchurch | Got an email saying they were sending someone, I wrote back saying the meeting was for the most senior level
1 | 2007-10-04 | A | BHCC | Alan McCarthy | He can't make it but will keep an eye on it and will send Alex Bailey in his place
1 | 2007-10-04 | A | Sussex Eye Hospital | Barbara Harris | She confirmed she is attending the Leader Workshop on 19th Oct
1 | 2007-10-05 | M | CCBH | Corrine Baker | Explained I had tried to invite Phil Fryer, the Principal but hadn't heard back - she asked for the information & will pass it onto him direct
1 | 2007-10-05 | M | Scope | Jan Foster | They have signed up to Engage West Sussex
1 | 2007-10-11 | A | Leader Presentation | Claire Mitchell | Worked on Leader Presentation
1 | 2007-10-15 | C | The Argus | James Lancaster | Talked about Leader, press coverage and The Argus involvement. He will chase Martin & Michael to see if they can make it. He will attend himself
1 | 2007-10-15 | C | All Leader Invities | Claire Mitchell | Chased all those that had expressed a desire to attend
1 | 2007-10-15 | C | DWP | Brendon Buckley | Alan Cave can't make the Leader meeting but will see if someone else can. JCP National Sales Team wanted to attend but advised that we're involving them on a local level
1 | 2007-10-18 | M | Welfare to Work | Angie Elliot Dickson
1 | 2007-10-18 | M | DEB | Kirsty Mackenzie | Catch up re Leader Workshop
1 | 2007-10-19 | M | Leader Presentation |  | Really good workshop - most of audience signed up on the spot. See notes
1 | 2007-11-12 | M | DEB | David Cain | To plan the West Sussex Employer Engagement Forum meeting - 13.11.07
1 | 2007-11-13 | M | WS EE Forum | David Cain | Meeting went well - Amanda B took minutes. They had some interesting ideas.
1 | 2007-11-14 | M | Sussex Eye Hospital | Barbara Harris | Presentation to their Trust Sub Committee on Diversity & Equality on Leader - went down well
1 | 2007-11-16 | M | Sussex Advice & Skills | Caroline Scott | Intro to WS EE Forum and discussion around Next Step Programme
1 | 2007-11-19 | M | Priory Partnership | Robin Feagan | Discussion around setting up an EE Category for these Awards, however the cost is £12K! He will let me know if this is possible. Informed of WS EE Forum
1 | 2007-11-19 | C | DEB | David Cain | Let him know about JCP Event next March - for an WS EE Stand and passed on Anne Parkinson and Richard Mccman from Arun District Council
1 | 2007-11-23 | M | Soton Leader Conference - Diversity Jig Saw | Hilary Wiseman | V. good conference, lots of fantastic speakers. They have between 160 - 180 employers attending
1 | 2007-11-28 | M | Leader Steering Group
25 | Total | 0